## Main Work CR
FORM W.C.36
(see para 251)
Estimate abstract report Report
(For all Original Works Costing Above Rs. 10,000)
Name of Scheme |  | Hon'ble Chief Minister Announcement | [6 empty] | D.H.O | 05.03.2019
Name of Work |  | Construction of Own Building to PEW unit at Attur in Salem District under the Hon'ble CM's announcement scheme | [6 empty] | D.D.C | 04.11.2019
Estimate No |  | CER .NO: 311/2018-2019 | [6 empty] | A.D.C | 12.10.2020
Estimate Amount |  | Rs.41,20,000.00 | [6 empty] | E.O.T
Agreement No |  | SE/NC/ 174/2018-2019
Agreement Amount |  | Rs. 34,47,580.54/-
Name of Contractor |  | M/s. Arumuka Construction
M. Book |  | 26940 A
File No |  | SLM/5708/2018
COMPLETION REPORT
Agt. No | Description | As Per Estimate |  |  | As Per Execution |  |  | Excess Amount | Savings Amount | Remarks
|  | Qty | Rate | Amt | Qty | Rate | Amt
1.1 | 1.1 : Earth work excavation in all soils (including refilling) a. 0 to 2 mt. | 43.9 | 134.6 | 5908.94 | 48.89 | 135 | 6600.15 | 691.21 |  | As per site requirement executed
1.3 | 1.3 : Earth work excavation in soft disintegrated rock (Including refilling) a. 0 to 2 mt. | 41 | 196.8 | 8068.8 | 10.71 | 196 | 2099.16 |  | 5969.64 | As per site requirement executed
1.5 | 1.5 : Earth work excavation for Open foundation (excluding refilling) a. 0 to 2 mt. | 80.6 | 63.6 | 5126.16 | 74.92 | 63 | 4719.96 |  | 406.2 | As per site requirement executed
1.6 | 1.6 : Earth work excavation for Open foundation for drains (excluding refilling) width upto 1.25 m a. 0 to 2 mt. | 4.2 | 95.4 | 400.68 |  | 95 | 0 |  | 400.68 | As per site requirement executed
2.1 | 2.1 : Filling sand | 29.7 | 707.3 | 21006.81 | 28.5 | 702 | 20007 |  | 999.81 | As per site requirement executed
2.6 | 2.6 : Supply and filling of 40mm HBSJ | 1.6 | 1172.24 | 1875.584 | 1.6 | 1170 | 1872 |  | 3.584 | As per site requirement executed
2.7 | 2.7 : Supply and filling of 20mm HBSJ | 1.6 | 1536.24 | 2457.984 | 1.6 | 1638 | 2620.8 | 162.816 |  | Excess due to high quoted tender rate
3.1 | 3.1 : C.C.1:5:10 for Foundation & Basement | 17.8 | 3261.88 | 58061.464 | 13.04 | 3261 | 42523.44 |  | 15538.024 | As per site requirement executed
3.2 | 3.2 : P.C.C. 1:2:4 for Foundation & Basement and other similar works | 5.9 | 4664.51 | 27520.609 | 5.57 | 4664 | 25978.48 |  | 1542.129 | As per site requirement executed
3.3 | 3.3 : P.C.C. 1:8:16 using 20 mm broken brick jelly | 0.2 | 2978.51 | 595.702 | 0 | 2978 | 0 |  | 595.702 | Item is not executed. Hence savings
6.2 | 6.2 : Brick work in C.M. 1:5 (F& B) using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") | 39.3 | 5093.03 | 200156.079 | 31.33 | 5400 | 169182 |  | 30974.079 | As per site requirement executed
7.2 | 7.2 : Supply and fixing of Bituminous filler pad, 20 mm tk. for expansion joint | 3.2 | 666 | 2131.2 | 2.2 | 666 | 1465.2 |  | 666 | As per site requirement executed
9.2 | 9.2 : Brick work in C.M. 1:6 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") a. In Ground Floor | 38.4 | 5084.74 | 195254.016 | 33.76 | 5800 | 195808 | 553.984 |  | Excess due to high quoted tender rate
| b. In First Floor | 13.6 | 5175.04 | 70380.544 | 11.76 | 6300 | 74088 | 3707.456 |  | Excess due to high quoted tender rate
10.2 | 10.2 : Brick partition work in C.M. 1:4 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") 114 mm tk (B.P.) a. In Foundation and basement | 36.2 | 625.9 | 22657.58 | 15.74 | 625 | 9837.5 |  | 12820.08 | As per site requirement executed
| b. In Ground Floor | 53.4 | 631.01 | 33695.934 | 71.15 | 631 | 44895.65 | 11199.716 |  | As per site requirement executed
| c. In First Floor | 58 | 641.3 | 37195.4 | 10.22 | 641 | 6551.02 |  | 30644.38 | As per site requirement executed
11.2 | 11.2 : Brick work in C.M. 1:4 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") 75 mm tk (B.P.) a. In Ground floor | 5 | 434.53 | 2172.65 | 5.18 | 434 | 2248.12 | 75.47 |  | Excess due to high quoted tender rate
13.1 | 13.1 : Filling with Excavated Earth | 68.8 | 22.2 | 1527.36 | 53.54 | 22 | 1177.88 |  | 349.48 | As per site requirement executed
21.2 | 21.2 : Teak wood Wrought & Put up a. T.W. over 2 m & below 3 m | 0.126 | 114146 | 14382.396 | 0.063 | 114146 | 7191.198 |  | 7191.198 | As per site requirement executed
| b. T.W. below 2 m length. | 0.093 | 102442 | 9527.106 | 0.12 | 102442 | 12293.04 | 2765.934 |  | As per site requirement executed
23.3 | 23.3 : S&F of Magnetic door catches | 7 | 52 | 364 | 6 | 52 | 312 |  | 52 | As per site requirement executed
24 | 24 : Manufacturing & supply of steel windows (Weight basis) | 1140.6 | 58 | 66154.8 | 1139.6 | 70 | 79772 | 13617.2 |  | Excess as per contractor's quoted rate
25 | 25 : M.S.Holdfast | 42 | 9.6 | 403.2 | 39 | 9 | 351 |  | 52.2 | As per site requirement executed
26 | 26 : Flooring in C.C.1:5:10 | 7.9 | 3261.88 | 25768.852 | 6.7 | 3261 | 21848.7 |  | 3920.152 | As per site requirement executed
28 | 28 : Floor plastering in C.M. 1:4, 20 mm tk. | 10.1 | 305.27 | 3083.227 | 10.73 | 305 | 3272.65 | 189.423 |  | Excess as per contractor's quoted rate
31 | 31 : Weathering course | 0.5 | 3202.37 | 1601.185 | 0.5 | 3202 | 1601 |  | 0.185 | As per site requirement executed
33 | 33 : Plastering in C.M. 1:5, 12 mm tk. | 926.2 | 148.17 | 137235.054 | 723.47 | 148 | 107073.56 |  | 30161.494 | As per site requirement executed
34 | 34 : Plastering in C.M. 1:4, 12 mm tk. | 60.8 | 153.74 | 9347.392 | 41.78 | 153 | 6392.34 |  | 2955.052 | As per site requirement executed
35 | 35 : Spl. Ceiling plastering in C.M. 1:3,10 mm tk. | 135 | 170.7 | 23044.5 | 141.39 | 170 | 24036.3 | 991.8 |  | Quantity is executed as per site requirements
36 | 36 : Cement mortar Border in C.M. 1:5, 12 mm tk. a. 150 mm wide | 79 | 45.71 | 3611.09 | 60.85 | 45 | 2738.25 |  | 872.84 | Quantity is executed as per site requirements
| b. 75 mm wide | 79 | 29.66 | 2343.14 | 60.85 | 29 | 1764.65 |  | 578.49 | Quantity is executed as per site requirements
| c. 50 mm wide | 79 | 22.06 | 1742.74 | 17.4 | 22 | 382.8 |  | 1359.94 | Quantity is executed as per site requirements
37.1 | 37.1 : White washing 3 coats (slaked) | 135 | 26.25 | 3543.75 | 141.39 | 26 | 3676.14 | 132.39 |  | Quantity is executed as per site requirements
39 | 39 : M.s Grills | 189 | 53.6 | 10130.4 | 348.8 | 53 | 18486.4 | 8356 |  | Quantity is executed as per site requirements
40 | 40 : Painting - New "wood work" | 33.8 | 162.42 | 5489.796 | 35.1 | 162 | 5686.2 | 196.404 |  | Quantity is executed as per site requirements
41 | 41 : Painting - New "iron work" | 63.3 | 96.93 | 6135.669 | 61.4 | 96 | 5894.4 |  | 241.269 | Quantity is executed as per site requirements
46 | 46 : S & F 20 mm dia Alu. Hanger Rod | 7.2 | 58 | 417.6 | 0 | 58 | 0 |  | 417.6 | Item is not executed. Hence savings
47 | 47 : S & F Alu Towel rail 75 cm long | 2 | 95 | 190 | 5 | 95 | 475 | 285 |  | Quantity is executed as per site requirements
48 | 48 : S & F 5 pin Coat stand | 3 | 55 | 165 | 6 | 55 | 330 | 165 |  | Quantity is executed as per site requirements
49 | 49 : S & F chromium plated 8 guage Picture Hook | 44 | 1.5 | 66 | 44 | 1 | 44 |  | 22 | Quantity is executed as per site requirements
50.2 | 50.2 : Providing precast Kerb stone in C.C. 1:3:6, 450 x 300 x 150 mm | 23 | 188.42 | 4333.66 | 22.45 | 188 | 4220.6 |  | 113.06 | Quantity is executed as per site requirements
50.3 | 50.3 : Supply and planting avenue trees | 5 | 272.64 | 1363.2 | 0 | 272 | 0 |  | 1363.2 | Quantity is executed as per site requirements
50.4 | 50.4 : Providing Tree guard | 5 | 649.4 | 3247 | 0 | 649 | 0 |  | 3247 | Quantity is executed as per site requirements
50.5 | 50.5 : Supplying. Fabricating and erection of M.S Scheme Name board | 1 | 13570.02 | 13570.02 | 0 | 13570 | 0 |  | 13570.02 | Quantity is executed as per site requirements
52 | 52 : PVC Water supply (ASTM) a. 32 mm dia | 12 | 168.56 | 2022.72 | 10.8 | 167 | 1803.6 |  | 219.12 | Quantity is executed as per site requirements
| b. 25 mm dia | 48 | 152.6 | 7324.8 | 33 | 151 | 4983 |  | 2341.8 | Quantity is executed as per site requirements
59.5 | 59.5 : Gully Trap using kiln burnt country bricks of size 23x11x7cm | 6 | 1225.43 | 7352.58 | 0 | 1225 | 0 |  | 7352.58 | Quantity is executed as per site requirements
60 | 60 : PVC Nahani trap (4way/2way) | 9 | 129.2 | 1162.8 | 4 | 129 | 516 |  | 646.8 | Quantity is executed as per site requirements
69 | Electrical arrangements 69 : 15 Amp. Power plug | 8 | 125 | 1000 | 8 | 125 | 1000 | 0 | 0 | Quantity is executed as per site requirements
72 | 72 : Box type Fibre Fan hook | 11 | 33.9 | 372.9 | 11 | 33 | 363 |  | 9.9 | Quantity is executed as per site requirements
74 | 74 : Charges for fixing of "Fan" | 11 | 347 | 3817 | 11 | 347 | 3817 | 0 | 0 | Quantity is executed as per site requirements
76 | 76 : 8 SWG wire | 15 | 18 | 270 | 5.6 | 18 | 100.8 |  | 169.2 | Quantity is executed as per site requirements
77.3 | 77.3 : S&F of TV/Telephone line Socket | 5 | 75 | 375 | 1 | 75 | 75 |  | 300 | Quantity is executed as per site requirements
77.4 | 77.4 : S&F of 20mm dia PVC pipe for TV/Telephone line | 50 | 58.07 | 2903.5 | 9.2 | 58 | 533.6 |  | 2369.9 | Quantity is executed as per site requirements
78 | 78 : Earthing Station IS3043 (Type I) | 1 | 2020 | 2020 | 1 | 2020 | 2020 | 0 | 0 | Quantity is executed as per site requirements
81 | 81 : Meter cupboard | 1.3 | 1959.1 | 2546.83 | 0.9 | 1959 | 1763.1 |  | 783.73 | Quantity is executed as per site requirements
86 | 86 : Anti termite treatment | 118 | 34 | 4012 | 92.7 | 34 | 3151.8 |  | 860.2 | Quantity is executed as per site requirements
112 | 112 : S & F of Exsaust Fan 300 mm dia | 4 | 1705 | 6820 | 4 | 1683 | 6732 |  | 88 | Quantity is executed as per site requirements
2.1.1 | ANNEXURE 2.1.1 : Supplying and filling with gravel | 36.1 | 258.3 | 9324.63 | 36.48 | 258 | 9411.84 | 87.21 |  | Quantity is executed as per site requirements
3.8 | 3.8 : PCC 1:4:8 using 40mm HBGS jelly | 3.5 | 3441.05 | 12043.675 | 2.16 | 3441 | 7432.56 |  | 4611.115 | Quantity is executed as per site requirements
8.1.1 | 8.1.1 : Standardised concrete Mix M20 Grade Concrete a. In Foundation and Basement | 27.7 | 5519.32 | 152885.164 | 22 | 5076 | 111672 |  | 41213.164 | Quantity is executed as per site requirements
| b) In Ground Floor. | 27.4 | 5587.32 | 153092.568 | 28.4 | 5094 | 144669.6 |  | 8422.968 | Quantity is executed as per site requirements
| c) In First Floor. | 15.8 | 5721.32 | 90396.856 | 10.46 | 5229 | 54695.34 |  | 35701.516 | Quantity is executed as per site requirements
14.1 | 14.1.II : Precast cupboard slab 40 mm tk using standardised concrete mix M20 grade. a. In Foundation & basement | 8.3 | 943.07 | 7827.481 | 6.32 | 943 | 5959.76 |  | 1867.721 | Quantity is executed as per site requirements
| b. In Ground Floor | 2.2 | 945.82 | 2080.804 | 0 | 945 | 0 |  | 2080.804 | Quantity is executed as per site requirements
18.1 | 18.1 : Formwork using M.S.Sheet a.For Column footings,plinth beam,Grade beam,Raftbeam,Raft slab etc., | 96 | 498.94 | 47898.24 | 100.84 | 396 | 39932.64 |  | 7965.6 | Quantity is executed as per site requirements
| b.Plain surfaces such as Roof slab,floorslab,Beams,lintels,lofts,sill slab,staircase,portico slab and other similar works | 344.2 | 573.61 | 197436.562 | 300.35 | 459 | 137860.65 |  | 59575.912 | Quantity is executed as per site requirements
| c.For Square and rectangular columns and small quantities | 137.4 | 688.33 | 94576.542 | 107.99 | 558 | 60258.42 |  | 34318.122 | Quantity is executed as per site requirements
| f.Curved surface | 49 | 860.42 | 42160.58 | 60.69 | 684 | 41511.96 |  | 648.62 | Quantity is executed as per site requirements
21.5.2 | 21.5.2 : Supply and fixing Solid UPVC door shutter with frame | 7.9 | 2670 | 21093 | 7.89 | 2670 | 21066.3 |  | 26.7 | Quantity is executed as per site requirements
21.6 | 21.6 : R.C.C.Door frames of size 100 x 75mm with one edge grooves size 't' x 20 mm using standardised concrete mix M20 grade. c. 1000 x 2100mm | 7 | 1731.26 | 12118.82 | 7 | 1724 | 12068 |  | 50.82 | Quantity is executed as per site requirements
23.1.1 | 23.1.1 : TW styles & rails with 9mm thick BWR single leaf shutters with brass screws c. 1000x2100 mm | 13 | 2824.42 | 36717.46 | 11.03 | 2824 | 31148.72 |  | 5568.74 | Quantity is executed as per site requirements
23.2.1 | 23.2.1 : 4mm thick pin headed Glass panels with Aluminium beedings | 28.1 | 639.5 | 17969.95 | 23.79 | 639 | 15201.81 |  | 2768.14 | Quantity is executed as per site requirements
29.8 | 29.8 : Glazed tiles using Grout (Tile Joint Filler) | 39.4 | 939.38 | 37011.572 | 30.22 | 939 | 28376.58 |  | 8634.992 | Quantity is executed as per site requirements
29.9 | 29.9 : Floor ceramic tiles using Grout (Tile Joint Filler) (antiskid) | 11.2 | 836.97 | 9374.064 | 11.13 | 836 | 9304.68 |  | 69.384 | Quantity is executed as per site requirements
31.2 | 31.2 : Finshing the top of Terrace floor with one course of solar reflective Ceramic tiles without base concrete | 111.8 | 1024.97 | 114591.646 | 91.64 | 1024 | 93839.36 |  | 20752.286 | Quantity is executed as per site requirements
38.6 | 38.6 : One coat white cement for new walls and other similar works. | 494 | 36.99 | 18273.06 | 384.6 | 36 | 13845.6 |  | 4427.46 | Quantity is executed as per site requirements
38.7 | 38.7 : Plastic Emulsion PAINT including primer for outer | 388.7 | 151.87 | 59031.869 | 291.3 | 153 | 44568.9 |  | 14462.969 | Quantity is executed as per site requirements
43.1 | 43.1 : Supply & Fabrication of Mild steel / RTS grills (without cement slurry) for all sizes of rods. | 8.41 | 61875 | 520368.75 | 7.631 | 59000 | 450229 |  | 70139.75 | Quantity is executed as per site requirements
44.2 | 44.2 : Rain water harvesting using defunct borewell and providing perforated cover slab a). Providing pit | 2 | 1245.89 | 2491.78 | 0 | 1000 | 0 |  | 2491.78 | Quantity is executed as per site requirements
| b) Augering 30cm dia | 6 | 298.95 | 1793.7 | 0 | 298 | 0 |  | 1793.7 | Quantity is executed as per site requirements
44.6 | 44.6 : PVC SWR 110 mm dia with ISI mark type- A for Rain water down fall pipe | 30.7 | 273.87 | 8407.809 | 22.5 | 273 | 6142.5 |  | 2265.309 | Quantity is executed as per site requirements
50.6 | 50.6 : Precast slab 50 mm tk.in C.C. 1:3:6 with fibre | 27.2 | 287.2 | 7811.84 | 16.8 | 287 | 4821.6 |  | 2990.24 | Quantity is executed as per site requirements
52.4 | 52.4 : 20mm dia PVC water supply ASTM pipe (fully consealed in walls) | 25 | 149.81 | 3745.25 | 15.2 | 149 | 2264.8 |  | 1480.45 | Quantity is executed as per site requirements
53.4 | 53.4 : S&F of C.I Manhole cover 60 x 60 cm (50kg weight ) | 1 | 1725 | 1725 | 1 | 1725 | 1725 | 0 | 0 | Quantity is executed as per site requirements
53.5 | 53.5 : Wash Hand Basin of size 550 x 400 mm | 4 | 2526.82 | 10107.28 | 4 | 2526 | 10104 |  | 3.28 | Quantity is executed as per site requirements
54.1.1 | 54.1.1 : S & F of 15mm dia half turn CP long body tap | 4 | 420 | 1680 | 4 | 472 | 1888 | 208 |  | Excess due to high quoted tender rate
54.2.1 | 54.2.1 : S & F of 15mm dia half turn CP short body tap | 5 | 372 | 1860 | 4 | 372 | 1488 |  | 372 | Quantity is executed as per site requirements
56.3.1 | 56.3.1 : S&F of Indian Water Closet white glazed (Oriya type) of size 580 x 440mm with PVC SWR grade P' or "S' trap - In G.F. | 2 | 2345.26 | 4690.52 | 2 | 2345 | 4690 |  | 0.52 | Quantity is executed as per site requirements
56.4.1 | 56.4.1 : S&F of Indian Water Closet white glazed (Oriya type) of size 580 x 440mm with PVC SWR grade P' or "S' trap - Other than G.F. | 1 | 3870.14 | 3870.14 | 1 | 3870 | 3870 |  | 0.14 | Quantity is executed as per site requirements
57.1.1 | 57.1.1 : S & F of E.W.C (White) 500mm with PVC SWR grade "P" or "S" Trap | 1 | 5127.8 | 5127.8 | 1 | 5127 | 5127 |  | 0.8 | Quantity is executed as per site requirements
58.3 | 58.3 : PVC SWR pipe (Soil line) with ISI mark - type 'B'. a. 110 mm dia. | 10.5 | 518.65 | 5445.825 | 9.2 | 518 | 4765.6 |  | 680.225 | Quantity is executed as per site requirements
| b. 75 mm dia. | 15 | 406.75 | 6101.25 | 9.8 | 406 | 3978.8 |  | 2122.45 | Quantity is executed as per site requirements
58.4 | 58.4 : Supplying, Laying & Concealing the 50mm dia PVC (SWR) pipe with ISI mark type - 'B' with relevant specials. | 6 | 81.2 | 487.2 | 5.6 | 81 | 453.6 |  | 33.6 | Quantity is executed as per site requirements
58.5 | 58.5 : PVC (SWR) pipe with ISI mark - type 'A' for ventilating shaft with cowl. | 1 | 439.4 | 439.4 | 1 | 439 | 439 |  | 0.4 | Quantity is executed as per site requirements
61.3 | 61.3 : UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003 a. 110 mm UPVC Non Pressure pipe | 51 | 336.42 | 17157.42 | 19.8 | 335 | 6633 |  | 10524.42 | Quantity is executed as per site requirements
| a. 160 mm UPVC Non Pressure pipe | 15 | 597.93 | 8968.95 | 0 | 220 | 0 |  | 8968.95 | Quantity is executed as per site requirements
62.1.1 | 62.1.1 : PVC Specials as per IS 10124/1982 Part II a. 110 mm dia PVC bend | 2 | 248 | 496 | 2 | 236 | 472 |  | 24 | As per Actual Execution
62.2.2 | 62.2.2 : PVC Equal Tee as per BIS 7834/1975 a. 110 mm dia PVC Equal tee | 2 | 303 | 606 | 1 | 289 | 289 |  | 317 | As per Actual Execution
64.1 | 64.1 : Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990. a. Light point with ceiling rose | 24 | 1070 | 25680 | 24 | 1070 | 25680 | 0 | 0 | As per Actual Execution
| b. Light point without ceiling rose | 12 | 1074 | 12888 | 12 | 1074 | 12888 | 0 | 0 | As per Actual Execution
| c. Calling bell point with Buzzer/Calling bell | 2 | 1102 | 2204 | 2 | 1102 | 2204 | 0 | 0 | As per Actual Execution
65.1 | 65.1 : Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for Fan point. | 11 | 1126 | 12386 | 11 | 1126 | 12386 | 0 | 0 | As per Actual Execution
66.1 | 66.1 : Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for Staircase Light Point. | 5 | 1973 | 9865 | 2 | 1973 | 3946 |  | 5919 | Quantity is executed as per site requirements
67.1 | 67.1 : Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for 5 amps 5 pin plug socket point @ Switch Board Itself. | 11 | 540 | 5940 | 11 | 540 | 5940 | 0 | 0 | As per Actual Execution
68.2 | 68.2 : Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for 5 amps 5 pin plug socket point @ Convenient Places. | 15 | 752 | 11280 | 15 | 752 | 11280 | 0 | 0 | As per Actual Execution
71.2 | 71.2 : Supplying and fixing of 32 AMPS Triple pole main switch. | 1 | 1340 | 1340 | 1 | 1340 | 1340 | 0 | 0 | As per Actual Execution
75.1.2 | 75.1.2 : Supply and delivery of 48" (1200 mm) Fan with ISI mark with Eletronic Dimmer | 11 | 1238.3 | 13621.3 | 11 | 1238 | 13618 |  | 3.3 | As per Actual Execution
77.6 | 77.6 : Run of 2 Wires of 4 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990. | 20 | 186 | 3720 | 0 | 186 | 0 |  | 3720 | As per Actual Execution
77.7 | 77.7 : Run of 2 Wires of 2.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990. | 58 | 155 | 8990 | 68.3 | 155 | 10586.5 | 1596.5 |  | Quantity is executed as per site requirements
79.2.1 | 79.2.1 : 3 Nos of 32 Amps - Fuse unit. | 2 | 600 | 1200 | 1 | 600 | 600 |  | 600 | Quantity is executed as per site requirements
80.1 | 80.1 : 450 x 375 x 20mm thick TW plank | 4 | 990 | 3960 | 2 | 990 | 1980 |  | 1980 | Quantity is executed as per site requirements
87.1 | 87.1 : Supplying and delivery of Three phase ELCB/RCCB | 2 | 2695 | 5390 | 1 | 2695 | 2695 |  | 2695 | Quantity is executed as per site requirements
98.3.2 | 98.3.2 : TW panelled door double Leaves shutter with brass fittings of size a. 1200 x 2100mm. (Crime & Traffic) | 2.3 | 5584.12 | 12843.476 | 2.2 | 4677 | 10289.4 |  | 2554.076 | Quantity is executed as per site requirements
344.2 | 344.2 : S&F of Bevelled edge mirror 500 x 400 x 5.5mm | 4 | 355 | 1420 | 4 | 355 | 1420 | 0 | 0 | Quantity is executed as per site requirements
361.5 | 361.5 : Vitrified Tiles flooring (ivory) | 85.6 | 912.13 | 78078.328 | 51.92 | 1188 | 61680.96 |  | 16397.368 | Quantity is executed as per site requirements
363.1 | 363.1 : Concrete Designer tile flooring | 50.9 | 1059.39 | 53922.951 | 85.9 | 912 | 78340.8 | 24417.849 |  | Quantity is executed as per site requirements
367 | 367 : Providing wooden (melamine) polish for new wood work | 5.2 | 997.28 | 5185.856 | 5.2 | 997 | 5184.4 |  | 1.456 | Quantity is executed as per site requirements
799 | 799 : Two coats of OBD over one coat white cement for inner walls | 494 | 75.46 | 37277.24 | 366.04 | 72 | 26354.88 |  | 10922.36 | Quantity is executed as per site requirements
|  |  |  | 3141933.011 |  |  | 2626995.048 | 69399.362 | 584337.325
| Add GST @ 12% |  |  | 377031.9613 |  |  | 315239.4058 | 8327.9234 | 70120.479
| Sub Total - I |  |  | 3518964.9723 |  |  | 2942234.4538 | 77727.2854 | 654457.804
| As Per Bill Roundoff | [5 empty] | -0.45 |  | 0.45
[7 empty] | 2942234.0038 | 77727.2854 | 654458.254
| Provision for External Electrical arrangements | L.S |  | 10000 |  |  |  |  | 10000
| Provision for Borewell and External Water supply arrangements | L.S |  | 30000 |  |  |  |  | 30000
| Provision for Drinking water supply | L.S |  | 10000 |  |  |  |  | 10000
| Provision for LED Lighting arrangements, Numbering and lettering and purchasing locks | L.S |  | 20000 |  |  |  |  | 20000
| Provision for Soil Investigation | L.S |  | 35000 |  |  |  |  | 35000
| Provision for Cupboard shutters | L.S |  | 30000 |  |  |  |  | 30000
| Sub Total - III |  |  | 3653964.9723 |  |  | 2942234.0038 | 77727.2854 | 789458.254
| Labour Welfare fund @ 1% |  |  | 36539.6497 |  |  | 26269 |  | 10270.6497
| Unforeseen items, contingencies and petty supervion charges @ 2.5% (Contingencies + NMR) |  |  | 91349.1243 |  |  | 2982 |  | 88367.1243
| Supervision charges @ 7.5% |  |  | 274047.3729 |  |  | 220667.5503 |  | 53379.8226
| Sub Total - IV |  |  | 4055901.1193 |  |  | 3192152.554 | 77727.2854 | 941475.8507
| Provision for Advertisement Charges | L.S |  | 20000 |  |  | 0 |  | 20000
| Provision for EB Deposits | L.S |  | 15000 |  |  | 13818 |  | 1182
| Provision for Planning Permission and Property tax | L.S |  | 16000 |  |  | 21642 | 5642
| Provision for Structural Design / Consultancy Charges | L.S |  | 13000 |  |  |  |  | 13000
| Quotation for Soil Test | L.S |  |  |  |  | 8300 | 8300
| Total - V |  |  | 4119901.1193 |  |  | 3235912.554 | 91669.2854 | 975657.8507
| Roundoff |  |  | 98.8807 |  |  |  |  | 98.8807
| Grand Total | Say |  | 4120000 |  |  | 3235912.554 | 91669.2854 | 975756.7314
|  | Savings |  | 884087.446
|  | Savings % |  | 21.4584
C.R Finalized for Rs.3235912.55 Which is Rs.884087.45 (or) 21.46 % Savings against the Estimate value of Rs.4120000.00 and recorded in Page No. 28 of M.Book No.24073 A.
JE /SLM |  | AEE/SLM |  |  | Divisional Accountant |  |  |  | Executive Engineer Salem Division