## New Abstract
Name of work :- Special repair works to Flat No.8B of CID Police quarters at Mandhaveli in Chennai City
Abstract
Sl. No | Item. No | Qty | Description of work | Rate | Unit | Amount
1 | 1.1 | 24.5 | Earth work excavation for foundation in all soils and sub soils to the required depth (including refilling) a) 0 to 2m depth | 247.31 | 1 Cum | 6059.095
2 | 15.1 | 4.6 | Providing Cuddappah slab of 20mm thick, finishing with two sides for cupboard, ward-robes, shelves, kitchen platform slabs, sink and other similar works I. 20mm thick In Ground Floor | 563.35 | 1 Sqm | 2591.41
3 | 74 | 7 | Electrical arrangement Charges for assembling and fixing of ceiling fan | 571 | 1 No | 3997
4 | 76 | 14 | Supply and run of 1 of No.8 SWG GI wire for earth connection | 26 | 1 Rmt | 364
5 | 77.4 | 25 | Supplying, laying and concealing of PVC pipe of 20mm dia | 87.66 | 1 Rmt | 2191.5
6 | 112 | 2 | Supplying and fixing of 300 mm dia sweep AC exhaust fan of approved ISI | 2336 | 1 No | 4672 |  | Annexure
7 | 238 | 0.525 | Anticorrosive treatment for steel grills | 4755.5 | 1 MT | 2496.6375
8 | 3.1.3 | 10.5 | ANNEXURE Plain cement concrete 1:5:10 (One of cement, five of crushed stone sand and ten of hard broken stone Jelly) for foundation using 40 mm gauge broken stone jelly | 4902.14 | 1 Cum | 51472.47
9 | 8.2.3.1 | 10.5 | Standardised concrete Mix M30 Grade Concrete b. In Ground floor | 8720.53 | 1 Cum | 91565.565
10 | 10.2.2 | 5 | Brick partition wall in C.M. 1:4 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") 114 mm thick (B.P.) b) In Ground Floor | 866.58 | 1 Sqm | 4332.9
11 | 21.5.2.2 | 3 | Supply and Fixing Soild UPVC door Shutter with frame | 3325 | 1 Sqm | 9975
12 | 22.5.1 | 54 | Supplying and fixing of following furniture fittings (ISI) make including cost of material and labour charges for fixing etc., all complete a) Butt Hinges with Nylon Washers of 75mm x 30mm (with required screws) | 64.5 | 1 No | 3483
13 |  | 18 | b) Tower Bolts of 150mm long and 12mm dia (with required screws) | 84.5 | 1 No | 1521
14 |  | 54 | c) Handles "D" type of 100mm long with required screws | 46 | 1 No | 2484
15 |  | 18 | d) Aluminium Door Stopper with Rubber Bush with required screws | 74 | 1 No | 1332
16 |  | 9 | e) Aldrops of 250mm long and 16mm dia with required screws, bolts and nuts | 235.5 | 1 No | 2119.5
17 | 29.9.4.1 | 4.2 | Supplying and laying of colour matt finish floor of size (305x305mm) and other similar works to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 1403.2 | 1 Sqm | 5893.44
18 | 29.9.5.1 | 23 | Supplying and laying of Colour matt finish wall tiles to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 1699.98 | 1 Sqm | 39099.54
19 | 33.2.1 | 8.5 | Plastering with CM 1:5 (One of cement and five of crushed stone sand) 12mm thick | 261.5 | 1 Sqm | 2222.75
20 | 43.2.1 | 0.525 | Supplying, fabricating and placing in position of Mild steel Grills / Ribbed Tor Steels binding wire insulated with PVC | 90322.8 | 1 MT | 47419.47
21 | 52.1.1 | 12 | Supplying, laying, fixing and jointing the following PVC pipes as per ASTM D - 1785 of schedule 40 of wall thickness not less than the specified in IS 4985 c) 20mm PVC pipe with necessary PVC/UPVC specials | 238.64 | 1 Rmt | 2863.68
22 | 57.1.2 | 1 | Supplying and fixing colour EWC superior variety ( colour) | 7651.85 | 1 No | 7651.85
23 | 58.3 | 10 | Supplying and fixing the following dia PVC (SWR) pipe including all required PVC specials etc., all complete., a) 110mm dia PVC SWR pipe | 735.27 | 1 Rmt | 7352.7
24 |  | 12 | b) 75mm dia PVC SWR pipe | 617.97 | 1 Rmt | 7415.64
25 | 60.1 | 5 | Supplying and fixing of PVC Nahani Trap not less than 75mm 4 way / 2 way (Superior variety) | 160 | 1 No | 800
26 | 61.3 | 18 | Supplying, laying and jointing the following dia UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003 a. 160 mm UPVC Non Pressure pipe | 815.71 | 1 Rmt | 14682.78
27 | 64.1.1 | 21 | Wiring with 1.5 Sqmm copper PVC insulated unsheathed single core 1.1 K.v. grade cable 5 amps flush type switch (Open wiring) a) Light point with ceiling rose | 895 | 1 No | 18795
28 | 67.1 | 7 | Wiring with 1.5 1 Sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for 5 amps 5 pin plug socket point @ Switch Board Itself. | 830 | 1 No | 5810
29 | 68.2.1 | 14 | Wiring with 1.5 sqmm copper P.V.C. insulated unsheathed single core 1.1.k.v. grade cable for 5 amps. 5 pin plug socket point at convenient places (Open wiring) | 677 | 1 No | 9478
30 | 69.2 | 9 | Supply and fixing of 15 Amps 3 pin plug socket point on a suitable PVC box concealed and covered with 3mm thick laminated hylem sheet | 135 | 1 No | 1215
32 | 70.5.2 | 15 | Supply and fixing of 4' long 18 W Crystal Glass LED tube Light with ISI mark | 690 | 1 No | 10350
33 | 71.3.2 | 1 | Supply and fixing of 32A DP switch of 500V with metal clad with fuse and neutral (side handle) on suitable TW board with earth connection | 1390 | 1 No | 1390
34 | 75.2 | 7 | Supply and delivery of following Electric Ceiling fan a) 48" Electric fan 1200mm sweep | 1553 | 1 No | 10871
35 | 77.7.1 | 80 | Run off mains with 2 wires of 2.5 Sqmm copper PVC insulated unsheathed single core 1.1KV cable (Open wiring) | 146.6 | 1 Rmt | 11728
31 | 84.3.1 | 129 | Supply and Run off main with 2 wires of 4 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable (Open wiring) | 177 | 1 Rmt | 22833
36 | 176.3.1 | 1 | Supply and fixing of 8 way single pole and neutral MCB sheet steel enclosure distribution board with double door (metal) | 3191 | 1 No | 3191
37 | 178 | 1 | Earthing as per the ISI specification with an earth electrode of 2.10 metre Class 'B' GI pipe of dia not less than 40mm with copper earth plate of size 125mm x 50mm x 6mm with necessary funneling arrangements | 2703 | 1 No | 2703
38 | 207.3.6 | 463 | Painting the old walls two coats with plastic emulsion paint of best approved quality colour and shade (Excluding scrapping) | 167 | 1 Sqm | 77321
39 | 207.3.9 | 463 | Painting one coat with ready mixed plastic emulsion paint primer for old wall of first class quality paint of approved colour and shade including thorough scrapping | 75 | 1 Sqm | 34725
40 | 207.4 | 104.1 | Painting the old wood work with two coats of approved Ist class synthetic enamel paint including thorough scrapping | 164 | 1 Sqm | 17072.4
41 | 209.7 | 128 | Clean removal of the existing damaged floor and wall plastering without damaged existing structure | 660 | 1 Sqm | 84480
42 | 222.2.1 | 24 | Labour charges for the removing and refixing the damaged door shutter or other similar joinery work | 383.9 | 1 Sqm | 9213.6
43 | 222.2.2 | 16.2 | Labour charges for the removing and refixing the damaged window shutter or other similar joinery work | 444.51 | 1 Sqm | 7201.062
44 | 362.2.2 | 115.5 | Supplying and fixing of Stain free nano polish Vitrified Tiles of size 600x600x8mm for flooring and other similar works | 1522.99 | 1 Sqm | 175905.345
45 | 379.5.2 | 1.4 | Supplying and laying of Jet black granite slab (Superfine polished with machine cut edges) of size 4'-0" x 2'-0" of 18 to 20mm thick for kitchen arrangements (Ground floor) | 1969.38 | 1 Sqm | 2757.132
46 | 383.4.3 | 1 | Supply, delivery and fixing of Stainless steel sink size of 600 x 450 x 200mm using 32mm dia ‘B’ class G.I. waste water pipe and 32 mm dia C.P. waste coupling | 7140 | 1 No | 7140
47 | 451.3.3 | 2 | Supplying and fixing of the following water supply fittings of approved make (ISI) and quality a) 15mm dia CP angle cock | 1002 | 1 No | 2004
48 |  | 1 | b) 15mm dia Stainless Steel Health Faucet | 1375 | 1 No | 1375
49 |  | 2 | c) 15mm dia SS Heavy Duty Long Body Tap | 1771 | 1 No | 3542
50 | 741.1.1 | 2 | Supply and fixing of 20Amps Double pole plug and sockets in sheet steel enclosure with 32 AMPS Double pole MCB in Flush with wall with earth connection ( for AC Plug) | 1839 | 1 No | 3678
51 | 753 | 2 | Construction of Inspection chamber with brickjelly cement concrete 1:8:16 ( One of cement, eight of crushed stone sand and sixteen of broken brick jelly 40mm gauge b.Inspection Chamber size 60 x 60 x 60 cm | 6248.08 | 1 No | 12496.16
52 | 832.5.3 | 1.1 | Supplying and fixing in position of UPVC Ventilator louvered ventilator type for all sizes | 8106 | 1 Sqm | 8916.6
53 | 983 | 10.5 | Providing and applying charges of Krystal Internal Membrane of Crystalline waterproofing admixture 3.2kg per one cum added in M30 grade reinforced cement concrete | 2080 | 1 Cum | 21840
54 | 983.1 | 41 | Providing waterproofing protective for outer wall using with applying two coats of forsoc bursh water proofing admixture over the existing walls and plastering with CM 1:2, 20mm thick | 1170 | 1 Sqm | 47970 | 0.0035
|  |  | Sub Total-I |  |  | 942060.2265
|  |  | GST @18% |  |  | 169570.8408
|  |  | Sub Total-II |  |  | 1111631.0673
|  |  | Labour welfare fund @ 1% |  |  | 9420.6023
|  |  | Provision for petty supervision and Contingencies @ 2.5% |  |  | 27790.7767
|  |  | Supervision charges @ 7.5% |  |  | 83372.33
|  |  | Total |  |  | 1232214.7763
[5 empty] | Say | 12,32,300/-

## codng
TENDER CODING SHEET (Rates to be filled up by the Tenderer in this coding sheet)
Name of work :- Special repair works to Flat No.8B of CID Police quarters at Mandhaveli in Chennai City
S. No | Item No | DESCRIPTION | QTY | UNIT | Rate exclusive of GST in Figures and in Words | AMOUNT
1 | 1.1 | Earth work excavation for foundation in all soils and sub soils to the required depth (including refilling) a) 0 to 2m depth | 24.5 | 1 Cum | 247.31 | 6059.095
2 | 15.1 | Providing Cuddappah slab of 20mm thick, finishing with two sides for cupboard, ward-robes, shelves, kitchen platform slabs, sink and other similar works I. 20mm thick In Ground Floor | 4.6 | 1 Sqm | 563.35 | 2591.41
3 | 74 | Electrical arrangement Charges for assembling and fixing of ceiling fan | 7 | 1 No | 571 | 3997
4 | 76 | Supply and run of 1 of No.8 SWG GI wire for earth connection | 14 | 1 Rmt | 26 | 364
5 | 77.4 | Supplying, laying and concealing of PVC pipe of 20mm dia | 25 | 1 Rmt | 87.66 | 2191.5
6 | 112 | Supplying and fixing of 300 mm dia sweep AC exhaust fan of approved ISI | 2 | 1 No | 2336 | 4672
7 | 238 | Anticorrosive treatment for steel grills | 0.525 | 1 MT | 4755.5 | 2496.6375
8 | 3.1.3 | ANNEXURE Plain cement concrete 1:5:10 (One of cement, five of crushed stone sand and ten of hard broken stone Jelly) for foundation using 40 mm gauge broken stone jelly | 10.5 | 1 Cum | 4902.14 | 51472.47
9 | 8.2.3.1 | Standardised concrete Mix M30 Grade Concrete b. In Ground floor | 10.5 | 1 Cum | 8720.53 | 91565.565
10 | 10.2.2 | Brick partition wall in C.M. 1:4 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") 114 mm thick (B.P.) b) In Ground Floor | 5 | 1 Sqm | 866.58 | 4332.9
11 | 21.5.2.2 | Supply and Fixing Soild UPVC door Shutter with frame | 3 | 1 Sqm | 3325 | 9975
12 | 22.5.1 | Supplying and fixing of following furniture fittings (ISI) make including cost of material and labour charges for fixing etc., all complete a) Butt Hinges with Nylon Washers of 75mm x 30mm (with required screws) | 54 | 1 No | 64.5 | 3483
13 |  | b) Tower Bolts of 150mm long and 12mm dia (with required screws) | 18 | 1 No | 84.5 | 1521
14 |  | c) Handles "D" type of 100mm long with required screws | 54 | 1 No | 46 | 2484
15 |  | d) Aluminium Door Stopper with Rubber Bush with required screws | 18 | 1 No | 74 | 1332
16 |  | e) Aldrops of 250mm long and 16mm dia with required screws, bolts and nuts | 9 | 1 No | 235.5 | 2119.5
17 | 29.9.4.1 | Supplying and laying of colour matt finish floor of size (305x305mm) and other similar works to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 4.2 | 1 Sqm | 1403.2 | 5893.44
18 | 29.9.5.1 | Supplying and laying of Colour matt finish wall tiles to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 23 | 1 Sqm | 1699.98 | 39099.54
19 | 33.2.1 | Plastering with CM 1:5 (One of cement and five of crushed stone sand) 12mm thick | 8.5 | 1 Sqm | 261.5 | 2222.75
20 | 43.2.1 | Supplying, fabricating and placing in position of Mild steel Grills / Ribbed Tor Steels binding wire insulated with PVC | 0.525 | 1 MT | 90322.8 | 47419.47
21 | 52.1.1 | Supplying, laying, fixing and jointing the following PVC pipes as per ASTM D - 1785 of schedule 40 of wall thickness not less than the specified in IS 4985 c) 20mm PVC pipe with necessary PVC/UPVC specials | 12 | 1 Rmt | 238.64 | 2863.68
22 | 57.1.2 | Supplying and fixing colour EWC superior variety ( colour) | 1 | 1 No | 7651.85 | 7651.85
23 | 58.3 | Supplying and fixing the following dia PVC (SWR) pipe including all required PVC specials etc., all complete., a) 110mm dia PVC SWR pipe | 10 | 1 Rmt | 735.27 | 7352.7
24 |  | b) 75mm dia PVC SWR pipe | 12 | 1 Rmt | 617.97 | 7415.64
25 | 60.1 | Supplying and fixing of PVC Nahani Trap not less than 75mm 4 way / 2 way (Superior variety) | 5 | 1 No | 160 | 800
26 | 61.3 | Supplying, laying and jointing the following dia UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003 a. 160 mm UPVC Non Pressure pipe | 18 | 1 Rmt | 815.71 | 14682.78
27 | 64.1.1 | Wiring with 1.5 Sqmm copper PVC insulated unsheathed single core 1.1 K.v. grade cable 5 amps flush type switch (Open wiring) a) Light point with ceiling rose | 21 | 1 No | 895 | 18795
28 | 67.1 | Wiring with 1.5 1 Sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for 5 amps 5 pin plug socket point @ Switch Board Itself. | 7 | 1 No | 830 | 5810
29 | 68.2.1 | Wiring with 1.5 sqmm copper P.V.C. insulated unsheathed single core 1.1.k.v. grade cable for 5 amps. 5 pin plug socket point at convenient places (Open wiring) | 14 | 1 No | 677 | 9478
30 | 69.2 | Supply and fixing of 15 Amps 3 pin plug socket point on a suitable PVC box concealed and covered with 3mm thick laminated hylem sheet | 9 | 1 No | 135 | 1215
31 | 70.5.2 | Supply and fixing of 4' long 18 W Crystal Glass LED tube Light with ISI mark | 15 | 1 No | 690 | 10350
32 | 71.3.2 | Supply and fixing of 32A DP switch of 500V with metal clad with fuse and neutral (side handle) on suitable TW board with earth connection | 1 | 1 No | 1390 | 1390
33 | 75.2 | Supply and delivery of following Electric Ceiling fan a) 48" Electric fan 1200mm sweep | 7 | 1 No | 1553 | 10871
34 | 77.7.1 | Run off mains with 2 wires of 2.5 Sqmm copper PVC insulated unsheathed single core 1.1KV cable (Open wiring) | 80 | 1 Rmt | 146.6 | 11728
35 | 84.3.1 | Supply and Run off main with 2 wires of 4 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable (Open wiring) | 129 | 1 Rmt | 177 | 22833
36 | 176.3.1 | Supply and fixing of 8 way single pole and neutral MCB sheet steel enclosure distribution board with double door (metal) | 1 | 1 No | 3191 | 3191
37 | 178 | Earthing as per the ISI specification with an earth electrode of 2.10 metre Class 'B' GI pipe of dia not less than 40mm with copper earth plate of size 125mm x 50mm x 6mm with necessary funneling arrangements | 1 | 1 No | 2703 | 2703
38 | 207.3.6 | Painting the old walls two coats with plastic emulsion paint of best approved quality colour and shade (Excluding scrapping) | 463 | 1 Sqm | 167 | 77321
39 | 207.3.9 | Painting one coat with ready mixed plastic emulsion paint primer for old wall of first class quality paint of approved colour and shade including thorough scrapping | 463 | 1 Sqm | 75 | 34725
40 | 207.4 | Painting the old wood work with two coats of approved Ist class synthetic enamel paint including thorough scrapping | 104.1 | 1 Sqm | 164 | 17072.4
41 | 209.7 | Clean removal of the existing damaged floor and wall plastering without damaged existing structure | 128 | 1 Sqm | 660 | 84480
42 | 222.2.1 | Labour charges for the removing and refixing the damaged door shutter or other similar joinery work | 24 | 1 Sqm | 383.9 | 9213.6
43 | 222.2.2 | Labour charges for the removing and refixing the damaged window shutter or other similar joinery work | 16.2 | 1 Sqm | 444.51 | 7201.062
44 | 362.2.2 | Supplying and fixing of Stain free nano polish Vitrified Tiles of size 600x600x8mm for flooring and other similar works | 115.5 | 1 Sqm | 1522.99 | 175905.345
45 | 379.5.2 | Supplying and laying of Jet black granite slab (Superfine polished with machine cut edges) of size 4'-0" x 2'-0" of 18 to 20mm thick for kitchen arrangements (Ground floor) | 1.4 | 1 Sqm | 1969.38 | 2757.132
46 | 383.4.3 | Supply, delivery and fixing of Stainless steel sink size of 600 x 450 x 200mm using 32mm dia ‘B’ class G.I. waste water pipe and 32 mm dia C.P. waste coupling | 1 | 1 No | 7140 | 7140
47 | 451.3.3 | Supplying and fixing of the following water supply fittings of approved make (ISI) and quality a) 15mm dia CP angle cock | 2 | 1 No | 1002 | 2004
48 |  | b) 15mm dia Stainless Steel Health Faucet | 1 | 1 No | 1375 | 1375
49 |  | c) 15mm dia SS Heavy Duty Long Body Tap | 2 | 1 No | 1771 | 3542
50 | 741.1.1 | Supply and fixing of 20Amps Double pole plug and sockets in sheet steel enclosure with 32 AMPS Double pole MCB in Flush with wall with earth connection ( for AC Plug) | 2 | 1 No | 1839 | 3678
51 | 753 | Construction of Inspection chamber with brickjelly cement concrete 1:8:16 ( One of cement, eight of crushed stone sand and sixteen of broken brick jelly 40mm gauge b.Inspection Chamber size 60 x 60 x 60 cm | 2 | 1 No | 6248.08 | 12496.16
52 | 832.5.3 | Supplying and fixing in position of UPVC Ventilator louvered ventilator type for all sizes | 1.1 | 1 Sqm | 8106 | 8916.6
53 | 983 | Providing and applying charges of Krystal Internal Membrane of Crystalline waterproofing admixture 3.2kg per one cum added in M30 grade reinforced cement concrete | 10.5 | 1 Cum | 2080 | 21840
54 | 983.1 | Providing waterproofing protective for outer wall using with applying two coats of forsoc bursh water proofing admixture over the existing walls and plastering with CM 1:2, 20mm thick | 41 | 1 Sqm | 1170 | 47970
[5 empty] | Total Amount Rs. | 942060.2265
( Rupees --------------------------------------------------------------------------------------------------------Only)
Note: The items not furnished with Quantity are deemed to be deleted.

## CS
REVISED COMPARATIVE STATEMENT
Name of work :- Special repair works to Flat No.8B of CID Police quarters at Mandhaveli in Chennai City
Sl. No. | ITEM No. | DESCRIPTION | QTY | UNIT | Estimate (As per PWD SR 2022-23) |  | M/s. P.Manickam & Co, Chennai - 600 012 |  | Thiru. P. Arul Chennai - 600 106 |  | The lowest and negotiated tenderer of M/s. P.Manickam & Co, Chennai - 600 012 vide Lr. Dt:20.01.2023 |  |  | Ab- Sub
[5 empty] | Rate | Amount | Rate | Amount | Rate | Amount | Rate |  | Amount
1 | 1.1 | Earth work excavation for foundation in all soils and sub soils to the required depth (including refilling) a) 0 to 2m depth | 24.5 | 1 Cum | 247.31 | 6059.095 | 250 | 6125 | 300 | 7350 | 250 |  | 6125 | 1.0877
2 | 15.1 | Providing Cuddappah slab of 20mm thick, finishing with two sides for cupboard, ward-robes, shelves, kitchen platform slabs, sink and other similar works I. 20mm thick In Ground Floor | 4.6 | 1 Sqm | 563.35 | 2591.41 | 560 | 2576 | 750 | 3450 | 560 |  | 2576 | -0.59466
3 | 74 | Electrical arrangement Charges for assembling and fixing of ceiling fan | 7 | 1 No | 571 | 3997 | 450 | 3150 | 450 | 3150 | 450 |  | 3150 | -21.1909
4 | 76 | Supply and run of 1 of No.8 SWG GI wire for earth connection | 14 | 1 Rmt | 26 | 364 | 25 | 350 | 30 | 420 | 25 |  | 350 | -3.8462
5 | 77.4 | Supplying, laying and concealing of PVC pipe of 20mm dia | 25 | 1 Rmt | 87.66 | 2191.5 | 100 | 2500 | 120 | 3000 | 100 |  | 2500 | 14.0771
6 | 112 | Supplying and fixing of 300 mm dia sweep AC exhaust fan of approved ISI | 2 | 1 No | 2336 | 4672 | 2300 | 4600 | 2500 | 5000 | 2300 |  | 4600 | -1.5411
7 | 238 | Anticorrosive treatment for steel grills | 0.525 | 1 MT | 4755.5 | 2496.6375 | 3000 | 1575 | 4500 | 2362.5 | 3000 |  | 1575 | -36.9152
8 | 3.1.3 | ANNEXURE Plain cement concrete 1:5:10 (One of cement, five of crushed stone sand and ten of hard broken stone Jelly) for foundation using 40 mm gauge broken stone jelly | 10.5 | 1 Cum | 4902.14 | 51472.47 | 4900 | 51450 | 4500 | 47250 | 4700 | RR | 49350 | -4.1235
9 | 8.2.3.1 | Standardised concrete Mix M30 Grade Concrete b. In Ground floor | 10.5 | 1 Cum | 8720.53 | 91565.565 | 8700 | 91350 | 9000 | 94500 | 8400 | RR | 88200 | -3.6756
10 | 10.2.2 | Brick partition wall in C.M. 1:4 using chamber Burnt bricks of size 23 x 11.4 x 7.5 cm (9" x 4 1/2"x 3") 114 mm thick (B.P.) b) In Ground Floor | 5 | 1 Sqm | 866.58 | 4332.9 | 900 | 4500 | 1000 | 5000 | 900 |  | 4500 | 3.8565
11 | 21.5.2.2 | Supply and Fixing Soild UPVC door Shutter with frame | 3 | 1 Sqm | 3325 | 9975 | 3300 | 9900 | 4000 | 12000 | 3300 |  | 9900 | -0.75188
12 | 22.5.1 | Supplying and fixing of following furniture fittings (ISI) make including cost of material and labour charges for fixing etc., all complete a) Butt Hinges with Nylon Washers of 75mm x 30mm (with required screws) | 54 | 1 No | 64.5 | 3483 | 60 | 3240 | 60 | 3240 | 60 |  | 3240 | -6.9767
13 |  | b) Tower Bolts of 150mm long and 12mm dia (with required screws) | 18 | 1 No | 84.5 | 1521 | 80 | 1440 | 80 | 1440 | 80 |  | 1440 | -5.3254
14 |  | c) Handles "D" type of 100mm long with required screws | 54 | 1 No | 46 | 2484 | 50 | 2700 | 50 | 2700 | 50 |  | 2700 | 8.6957
15 |  | d) Aluminium Door Stopper with Rubber Bush with required screws | 18 | 1 No | 74 | 1332 | 70 | 1260 | 70 | 1260 | 70 |  | 1260 | -5.4054
16 |  | e) Aldrops of 250mm long and 16mm dia with required screws, bolts and nuts | 9 | 1 No | 235.5 | 2119.5 | 240 | 2160 | 300 | 2700 | 240 |  | 2160 | 1.9108
17 | 29.9.4.1 | Supplying and laying of colour matt finish floor of size (305x305mm) and other similar works to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 4.2 | 1 Sqm | 1403.2 | 5893.44 | 1400 | 5880 | 1300 | 5460 | 1400 |  | 5880 | -0.22805
18 | 29.9.5.1 | Supplying and laying of Colour matt finish wall tiles to the required size wherever necessary, pointing the joints with Grout (Tile joint filler) | 23 | 1 Sqm | 1699.98 | 39099.54 | 1600 | 36800 | 1800 | 41400 | 1600 |  | 36800 | -5.8812
19 | 33.2.1 | Plastering with CM 1:5 (One of cement and five of crushed stone sand) 12mm thick | 8.5 | 1 Sqm | 261.5 | 2222.75 | 260 | 2210 | 260 | 2210 | 260 |  | 2210 | -0.57361
20 | 43.2.1 | Supplying, fabricating and placing in position of Mild steel Grills / Ribbed Tor Steels binding wire insulated with PVC | 0.525 | 1 MT | 90322.8 | 47419.47 | 90000 | 47250 | 100000 | 52500 | 87500 | RR | 45937.5 | -3.1252
21 | 52.1.1 | Supplying, laying, fixing and jointing the following PVC pipes as per ASTM D - 1785 of schedule 40 of wall thickness not less than the specified in IS 4985 c) 20mm PVC pipe with necessary PVC/UPVC specials | 12 | 1 Rmt | 238.64 | 2863.68 | 235 | 2820 | 240 | 2880 | 235 |  | 2820 | -1.5253
22 | 57.1.2 | Supplying and fixing colour EWC superior variety ( colour) | 1 | 1 No | 7651.85 | 7651.85 | 7650 | 7650 | 8000 | 8000 | 7650 |  | 7650 | -0.024177
23 | 58.3 | Supplying and fixing the following dia PVC (SWR) pipe including all required PVC specials etc., all complete., a) 110mm dia PVC SWR pipe | 10 | 1 Rmt | 735.27 | 7352.7 | 750 | 7500 | 700 | 7000 | 750 |  | 7500 | 2.0033
24 |  | b) 75mm dia PVC SWR pipe | 12 | 1 Rmt | 617.97 | 7415.64 | 610 | 7320 | 600 | 7200 | 610 |  | 7320 | -1.2897
25 | 60.1 | Supplying and fixing of PVC Nahani Trap not less than 75mm 4 way / 2 way (Superior variety) | 5 | 1 No | 160 | 800 | 160 | 800 | 160 | 800 | 160 |  | 800 | 0
26 | 61.3 | Supplying, laying and jointing the following dia UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003 a. 160 mm UPVC Non Pressure pipe | 18 | 1 Rmt | 815.71 | 14682.78 | 1000 | 18000 | 1000 | 18000 | 1000 |  | 18000 | 22.5926
27 | 64.1.1 | Wiring with 1.5 Sqmm copper PVC insulated unsheathed single core 1.1 K.v. grade cable 5 amps flush type switch (Open wiring) a) Light point with ceiling rose | 21 | 1 No | 895 | 18795 | 900 | 18900 | 1000 | 21000 | 900 |  | 18900 | 0.55866
28 | 67.1 | Wiring with 1.5 1 Sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming IS: 694:1990 for 5 amps 5 pin plug socket point @ Switch Board Itself. | 7 | 1 No | 830 | 5810 | 830 | 5810 | 830 | 5810 | 830 |  | 5810 | 0
29 | 68.2.1 | Wiring with 1.5 sqmm copper P.V.C. insulated unsheathed single core 1.1.k.v. grade cable for 5 amps. 5 pin plug socket point at convenient places (Open wiring) | 14 | 1 No | 677 | 9478 | 700 | 9800 | 675 | 9450 | 700 |  | 9800 | 3.3973
30 | 69.2 | Supply and fixing of 15 Amps 3 pin plug socket point on a suitable PVC box concealed and covered with 3mm thick laminated hylem sheet | 9 | 1 No | 135 | 1215 | 130 | 1170 | 130 | 1170 | 130 |  | 1170 | -3.7037
31 | 70.5.2 | Supply and fixing of 4' long 18 W Crystal Glass LED tube Light with ISI mark | 15 | 1 No | 690 | 10350 | 690 | 10350 | 690 | 10350 | 690 |  | 10350 | 0
32 | 71.3.2 | Supply and fixing of 32A DP switch of 500V with metal clad with fuse and neutral (side handle) on suitable TW board with earth connection | 1 | 1 No | 1390 | 1390 | 1390 | 1390 | 1390 | 1390 | 1390 |  | 1390 | 0
33 | 75.2 | Supply and delivery of following Electric Ceiling fan a) 48" Electric fan 1200mm sweep | 7 | 1 No | 1553 | 10871 | 1550 | 10850 | 1550 | 10850 | 1550 |  | 10850 | -0.19317
34 | 77.7.1 | Run off mains with 2 wires of 2.5 Sqmm copper PVC insulated unsheathed single core 1.1KV cable (Open wiring) | 80 | 1 Rmt | 146.6 | 11728 | 150 | 12000 | 150 | 12000 | 150 |  | 12000 | 2.3192
35 | 84.3.1 | Supply and Run off main with 2 wires of 4 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable (Open wiring) | 129 | 1 Rmt | 177 | 22833 | 177 | 22833 | 177 | 22833 | 175 | RR | 22575 | -1.1299
36 | 176.3.1 | Supply and fixing of 8 way single pole and neutral MCB sheet steel enclosure distribution board with double door (metal) | 1 | 1 No | 3191 | 3191 | 3190 | 3190 | 3190 | 3190 | 3190 |  | 3190 | -0.031338
37 | 178 | Earthing as per the ISI specification with an earth electrode of 2.10 metre Class 'B' GI pipe of dia not less than 40mm with copper earth plate of size 125mm x 50mm x 6mm with necessary funneling arrangements | 1 | 1 No | 2703 | 2703 | 2700 | 2700 | 2700 | 2700 | 2700 |  | 2700 | -0.11099
38 | 207.3.6 | Painting the old walls two coats with plastic emulsion paint of best approved quality colour and shade (Excluding scrapping) | 463 | 1 Sqm | 167 | 77321 | 165 | 76395 | 165 | 76395 | 165 |  | 76395 | -1.1976
39 | 207.3.9 | Painting one coat with ready mixed plastic emulsion paint primer for old wall of first class quality paint of approved colour and shade including thorough scrapping | 463 | 1 Sqm | 75 | 34725 | 80 | 37040 | 82 | 37966 | 74 | RR | 34262 | -1.3333
40 | 207.4 | Painting the old wood work with two coats of approved Ist class synthetic enamel paint including thorough scrapping | 104.1 | 1 Sqm | 164 | 17072.4 | 165 | 17176.5 | 165 | 17176.5 | 165 |  | 17176.5 | 0.60976
41 | 209.7 | Clean removal of the existing damaged floor and wall plastering without damaged existing structure | 128 | 1 Sqm | 660 | 84480 | 660 | 84480 | 660 | 84480 | 640 | RR | 81920 | -3.0303
42 | 222.2.1 | Labour charges for the removing and refixing the damaged door shutter or other similar joinery work | 24 | 1 Sqm | 383.9 | 9213.6 | 380 | 9120 | 380 | 9120 | 380 |  | 9120 | -1.0159
43 | 222.2.2 | Labour charges for the removing and refixing the damaged window shutter or other similar joinery work | 16.2 | 1 Sqm | 444.51 | 7201.062 | 440 | 7128 | 440 | 7128 | 440 |  | 7128 | -1.0146
44 | 362.2.2 | Supplying and fixing of Stain free nano polish Vitrified Tiles of size 600x600x8mm for flooring and other similar works | 115.5 | 1 Sqm | 1522.99 | 175905.345 | 1520 | 175560 | 1520 | 175560 | 1470 | RR | 169785 | -3.4793
45 | 379.5.2 | Supplying and laying of Jet black granite slab (Superfine polished with machine cut edges) of size 4'-0" x 2'-0" of 18 to 20mm thick for kitchen arrangements (Ground floor) | 1.4 | 1 Sqm | 1969.38 | 2757.132 | 1960 | 2744 | 1960 | 2744 | 1960 |  | 2744 | -0.47629
46 | 383.4.3 | Supply, delivery and fixing of Stainless steel sink size of 600 x 450 x 200mm using 32mm dia ‘B’ class G.I. waste water pipe and 32 mm dia C.P. waste coupling | 1 | 1 No | 7140 | 7140 | 7140 | 7140 | 7140 | 7140 | 7140 |  | 7140 | 0
47 | 451.3.3 | Supplying and fixing of the following water supply fittings of approved make (ISI) and quality a) 15mm dia CP angle cock | 2 | 1 No | 1002 | 2004 | 1000 | 2000 | 1000 | 2000 | 1000 |  | 2000 | -0.1996
48 |  | b) 15mm dia Stainless Steel Health Faucet | 1 | 1 No | 1375 | 1375 | 1375 | 1375 | 1375 | 1375 | 1375 |  | 1375 | 0
49 |  | c) 15mm dia SS Heavy Duty Long Body Tap | 2 | 1 No | 1771 | 3542 | 1770 | 3540 | 1770 | 3540 | 1770 |  | 3540 | -0.056465
50 | 741.1.1 | Supply and fixing of 20Amps Double pole plug and sockets in sheet steel enclosure with 32 AMPS Double pole MCB in Flush with wall with earth connection ( for AC Plug) | 2 | 1 No | 1839 | 3678 | 1840 | 3680 | 1840 | 3680 | 1840 |  | 3680 | 0.054377
51 | 753 | Construction of Inspection chamber with brickjelly cement concrete 1:8:16 ( One of cement, eight of crushed stone sand and sixteen of broken brick jelly 40mm gauge b.Inspection Chamber size 60 x 60 x 60 cm | 2 | 1 No | 6248.08 | 12496.16 | 6250 | 12500 | 6250 | 12500 | 6250 |  | 12500 | 0.030729
52 | 832.5.3 | Supplying and fixing in position of UPVC Ventilator louvered ventilator type for all sizes | 1.1 | 1 Sqm | 8106 | 8916.6 | 8100 | 8910 | 8100 | 8910 | 8100 |  | 8910 | -0.074019
53 | 983 | Providing and applying charges of Krystal Internal Membrane of Crystalline waterproofing admixture 3.2kg per one cum added in M30 grade reinforced cement concrete | 10.5 | 1 Cum | 2080 | 21840 | 2000 | 21000 | 2000 | 21000 | 2000 |  | 21000 | -3.8462
54 | 983.1 | Providing waterproofing protective for outer wall using with applying two coats of forsoc bursh water proofing admixture over the existing walls and plastering with CM 1:2, 20mm thick | 41 | 1 Sqm | 1170 | 47970 | 1170 | 47970 | 1170 | 47970 | 1150 | RR | 47150 | -1.7094
|  | Total Amount Rs. |  |  |  | 942060.2265 |  | 941857.5 |  | 959700 |  |  | 923104
|  | GST @ 18% |  |  |  | 169570.8408 |  | 169534.35 |  | 172746 |  |  | 166158.72
|  | TOTAL |  |  |  | 1111631.0673 |  | 1111391.85 |  | 1132446 |  |  | 1089262.72
|  | Excess / Less amount | [5 empty] | -239.2173 |  | 20814.9327 |  |  | -22368.3473
|  | Excess / Less percentage | [5 empty] | -0.021519 |  | 1.8725 |  |  | -2.0122
Submitted : The lowest and negotiated tender of M/s. P.Manickam & Co, Chennai - 600 012, for a value of Rs.10,89,262.72 (with GST at 18%) which is (-) Rs.22,368.35 or at (-)2.01% less than the estimate value for Rs.11,11,631.07 (with GST at 18%) as per PWD SR 2022-2023 may be accepted by the Superintending Engineer/Chennai Circle.
Superintending Engineer Chennai Circle / TNPHC Ltd.,

## Ann-A
Name of work :- Special repair works to Flat No.8B of CID Police quarters at Mandhaveli in Chennai City
ANNEXURE TO SCHEDULE - A
Sl. No | Item No | QTY | DESCRIPTION OF WORK | TNBP NO. | RATE IN FIG. AND IN WORDS | UNIT IN FIG. AND IN WORDS | AMOUNT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | 1.1 |  | Earth work excavation for foundation in all soils and sub-soils to the required depth as may be directed except in hard rock requiring blasting but inclusive of shoring, strutting, and bailing out water wherever necessary and refilling the sides of foundation with excavated earth in 150mm thick layers well watered rammed and consolidated and depositing the surplus earth in places shown clearing and levelling the site with an initial lead of 10 metres and lift as specified here under etc. complete in all respects complying with relevant standard specifications. (Including Refilling). a) 0 to 2m depth. | 17, 23 & 24 |  | 1m3 (One Cubic metre)
2 | 15.1 |  | Providing Cuddappah slab of 20mm thick, finishing with two sides for cupboard, ward-robes, shelves, kitchen platform slabs, sink and other similar works including finishing and fixing in position complying with relevant Standard specifications etc., complete in the following floors (Measurement will be taken including bearing also) as directed by the departmental officers (Quality of Cuddappah slab shall be got approved by the Executive Engineer before fixing. I. 20mm thick In Ground Floor |  |  | 1m2 (One Square metre)
3 | 74 |  | Charges for assembling and fixing of ceiling fan of different sweep with necessary connections and fixing of fan regulator on the existing board etc., all complete (Excluding cost of fan) |  |  | 1 No. ( One Number )
4 | 76 |  | Supplying and laying of 8SWG GI wire on wall below ground levels with necessary ‘U’ Nails, earth work excavation and refilling etc... including cost of all materials etc.. all complete. |  |  | 1 RMT (One Running Metre)
5 | 77.4 |  | Supplying, laying and concealing of PVC pipe of 20mm dia with necessary specials and other materials including Run off 1No. Fish wire (G.I.22g) for drawing cable for T.V./Telephone etc., all complete and as directed by the departmental officers. |  |  | 1 RMT (One Running Metre)
6 | 112 |  | Supplying and fixing of 300 mm dia sweep AC exhaust fan of approved ISI quality including necessary wall opening, fixing and finishing the wall opening and making good including cost of material, labour for fixing, chipping and redoing necessary inter connection, scaffolding, hire charges for tools and plants etc., all complete and as directed by the departmental officers. |  |  | 1 No. ( One Number )
7 | 238 |  | Applying one coat of anticorrosive treatment on steel reinforcement rods (20 ltrs. of anitcorrosive chemical for one mertic tonne of steel reinforcement rods) at site including a cost of required quantity of anticorrosive chemicals, (best approved quality) cement, consumables such as brushes, gloves and labour for anticorrosive coating etc. complete and as directed by the departmental officers. (The Quality and brand of anticorrosive chemaical should be got approved by the Executive Engineer before use). |  |  | 1 MT ( One Metric tonne )
8 | 3.1.3 |  | ANNEXURE Plain cement concrete 1:5:10 (One of cement, five of crushed stone sand and ten of hard broken stone Jelly) for foundation using 40 mm gauge hard broken stone jelly inclusive of shoring, strutting and bailing out water wherever necessary ramming, curing etc., complete in all respects complying with relevant standard specifications and as directed by the departmental officers. |  |  | 1m3 ( One Cubic metre )
9 | 8.2.3.1 |  | Providing and laying in position, Standardised Concrete Mix M-30 Grade in accordance with IS:456-2000 using 20mm and down graded hard broken granite stone jelly for the all RCC items of works with minimum cement content of 400 Kg/m3 and maximum water cement ratio of 0.45, including admixture (plasticiser/super plasticiser) in recommended proportions as per IS:9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability with about (5.0 cum) 7730Kg of 20mm machine crushed stone jelly and with about (3.3 cum) 5156 Kg of 10-12mm machine crushed stone jelly and with about (4.79 cum) 7670Kg of crushed stone sand (for making 10 cum) but excluding cost of reinforcement grill and fabricating charges, centering and shuttering and also including laying, vibrating with mechanical vibrators, finishing, curing etc., and providing fixtures like fan clamps in the RCC floor/roof slabs wherever necessary without claiming extra etc., complete complying with relevent standard specification and as directed by the departmental officers. The coarse and fine aggregates to be used should comply with requirements of IS standards. (No separate payment will be made by the Departmental for the excess usage of materials) b. In Ground floor |  |  | 1m3 (One Cubic metre)
10 | 10.2.2 |  | Brick partition wall in Cement Mortar 1:4 (One of cement and four of crushed stone sand,) 114mm thick for super structure in the following floors using chamber burnt bricks of size 9”x4½"x3” (23x11.4x7.5cm) including labour for fixing the doors, windows and ventilator frames in position, fixing of hold fasts, scaffoldings, curing etc., complete in all respect complying with relevant standard specifications and drawings b) In Ground floor |  |  | 1m2 (One Square metre)
11 | 21.5.2.2 |  | Providing and fixing factory made unplasticized polyvinyl chloride (UPVC) Door Frame of size 50X47mm with a wall thickness of 5mm, made out extruded 5mm rigid UPVC foam sheet, mitred at two corners and joined with 2 nos of 150mm long brackets of 15X15mm M.S square tube. The two vertical and horizontal door profiles are to be reinforced with 19X19mm M.S Square tube of 19 gauge with primer coat. The door frame shall be fixed to the wall using 65/100mm long M.S screw through the frame by using PVC fasteners. A minimum of 4 nos screws to be provided for each vertical member & minimum 2 nos for horizontal member etc., and providing and fixing 30mm thick factory made door shutter with unplasticized polyvinyl chloride (UPVC) solid panel foam sheet , structured with M.S. tube of 19 gauge thickness and size 19 x 19mm for styles & 15mm x 15mm for top & bottom rails. Panelling of 5mm thick UPVC One Side Printed Lamination single sheet to be fitted in the M.S. frame welded / sealed to the styles and rails covered with 5mm thick heat moulded UPVC "C" channel of 30 x 50mm and 5mm thick, 75mm wide UPVC sheet for top rail, lock rail and bottom rail on either side and 10mm (5mm X 2 Nos) thick, 20mm wide cross UPVC sheet as gap insert for top rail & bottom rail and joined together with PVC solvent cement adhesive. An additional 5mm thick UPVC strip of 20mm width is to be stuck on the interior side of the 'C' Channel using PVC solvent cement adhesive including cost and labour charges for fixing of 3 nos 4” SS butt hinges and Aluminium furniture fittings such as 1 No 4" Tower bolt, 1 No 5" Aldrop, 2 Nos 6" flat 'D' type Handle etc are included the fitting provided shall bear ISI marks. (The quality and brand of door shutter and furniture fittings should be got approved from the Executive Engineer before use) |  |  | 1m2 (One Square metre)
12 | 22.5.2 |  | Supplying and fixing of following furniture fittings of approved make ISI including cost of materials and labour charges for fixing etc., all complete as directed by the departemntal officers. (The furniture fittings should be got approved from the Executive Engineer before use) a) Butt Hinges with Nylon Washers of 75mm x 30mm (with required screws) |  |  | 1 No. ( One Number )
13 |  |  | b) Tower Bolts of 150mm long and 12mm dia (with required screws) |  |  | 1 No. ( One Number )
14 |  |  | c) Handles "D" type of 100mm long with required screws |  |  | 1 No. ( One Number )
15 |  |  | d) Aluminium Door Stopper with Rubber Bush with required screws |  |  | 1 No. ( One Number )
16 |  |  | e) Aldrops of 250mm long and 16mm dia with required screws, bolts and nuts |  |  | 1 No. ( One Number )
17 | 29.9.4.1 |  | Supplying and laying of Colour matt finish floor Tiles of size 305x305mm (12"x12") for flooring and other similar works (Best approved superior quality and the same shall be got approved from the Executive Engineer before using) over cement mortor 1:3 (One of cement and three of crushed stone sand) 20mm thick including fixing in position, cutting the tiles to the required size wherever necessary pointing the joints with Grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand quality of tiles should be got approved from Executive Engineer before use). |  |  | 1m2 (One Square metre)
18 | 29.9.5.1 |  | Supplying and fixing of Colour matt finish Wall Tiles of size 12"x18" for wall and other similar works (Best approved superior quality and the same shall be got approved from the Executive Engineer before using) over cement plastering in CM 1:2 (One of cement and two of crushed stone sand) 10mm thick including fixing in position, cutting the tiles to the required size wherever necessary, pointing the joints with Grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand quality of tiles should be got approved from Executive Engineer before use ). |  |  | 1m2 (One Square metre)
19 | 33.2.1 |  | Plastering with CM 1:5 (One of cement and five of crushed stone sand) 12mm thick finished with neat cement including plasticizer, providing band cornice, ceiling cornice, curing, scaffolding, etc., complete in all respects and complying with relevant standard specifications. |  |  | 1m2 (One Square metre)
20 | 43.2.1 |  | Supplying, fabricating and placing in position of Mild steel Grills / Ribbed Tor Steels (without cement slurry) of all diameters for reinforcement for all floors including cost of binding wire insulated with PVC, bending tying etc., all complete and as directed by the departmental officers. |  |  | 1 MT (One Metric Tonne)
21 | 52.1.1 |  | Supplying, laying, fixing and jointing the following PVC pipes as per ASTM D - 1785 of schedule 40 of wall thickness not less than the specified in IS 4985 suitable for plumbing by threading of wall thickness including the cost of suitable UPVC specials like Elbow, Tee reducers, Plug, unions, bend, coupler, nipple/ UPVC gate valve, UPVC check and UPVC / ball valve etc., wherever required above the ground level including the cost of teflon tape, PVC special clamps, nails, etc., fixing on wall to the proper gradient and alignment and redoing the chipped of masonry etc., as directed by the departmental officers. (The brand and quality of pipes and specials should be got approved by the EE/SE/CE before use in works) c) 20mm dia ASTM D schedule 40 threaded PVC pipe with necessary UPVC specials |  |  | 1 RMT (One Running Metre)
22 | 57.1.2 |  | Supplying and fixing EWC superior variety (Colour) 500mm with PVC SWR grade 'P' or 'S' trap including cost and fixing of double flapped coloured plastic sheet cover PVC flushing cistern in appropriate level as directed by the departmental officers at a maximum level of 5’6” and of approved brand of 10litres capacity including fittings such as CI brackets. PVC connection GM wheel valve, Hex nipple, etc., complete (The Quality and brand of EWC and plastic cover shall be got approved from the Executive Engineer before fixing) |  |  | 1 No. ( One Number )
23 | 58.3 |  | Supplying and fixing the following dia PVC (SWR) pipe with ISI mark confirming to IS 13952:1992- type 'B' for soil line with relevant specials confirming to IS 14735 including jointing with seal ring confirming to IS 5382 with leaving a gap about 10mm to allow thermal expansion,fixing the pipes into walls with necessary wooden plug, screws, holding wherever necessary and making good of the dismantled portion with necessary connections to sanitary fittings etc., complete in all respects and as directed by the departmental officers. a) 110mm dia PVC SWR pipe including all required PVC specials etc., all complete., |  |  | 1 RMT (One Running Metre)
24 |  |  | b) 75mm dia PVC SWR pipe including all required PVC specials etc., all complete., |  |  | 1 RMT (One Running Metre)
25 | 60.1 |  | Supplying and fixing of PVC Nahani Trap not less than 75mm 4 way / 2 way (Superior variety) having minimum of water seal of 50mm confirm to relevant I.S. specifications with its latest amendments including resting on the bed of brick jelly concrete 1:5:10 (One of cement, five of crushed stone sand and ten of 40 mm gauge brick jelly) etc., complete as directed by the departmental officers (The PVC Nahani Trap should be got approved from the Executive Engineer before use) | 102 |  | 1 No. ( One Number )
26 | 61.3 |  | Supplying, laying and jointing the following dia UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003, superior variety and tested with water, including necessary earth work excavation for trenches and refilling the same, well rammed and consolidated after the pipes are jointed and laid to proper gradiant to the alignment as directed by the departmental officers. (SN8 SDR 34 (S16.5), as per IS 15328/2003, should be got approved by the EE/SE/CE before use in works) a. 160 mm UPVC Non Pressure pipe |  |  | 1 RMT (One Running Metre)
27 | 64.1.1 |  | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark conforming to IS: 694/1990, 1.1K.v. grade cable with continuous earth by means of 1.5sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark conforming to IS: 694/1990, 1.1 k.v . grade cable in surface run of PVC rigid conduit pipe heavy duty with ISI mark with suitable size TW switch box required thickness concealed and covered with 3 mm thick laminated hylem sheet controlled by 5Amps flush type switch including circuit mains cost of all materials, specials etc., all complete.(Open wiring) a. Light point with ceiling rose |  |  | 1 No. ( One Number)
28 | 67.1 |  | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable with continuous earth by means of 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cablewith ISI mark confirming to IS: 694/1990,1.1.k.v. grade cable in fully concealed PVC rigid conduit pipe heavy duty with ISI mark with suitable size MS box of 16g thick concealed and covered with 3mm thick laminated hylem sheet for 5 amps 5 pin plug socket point at Switch Board Itself including circuit mains, cost of all materials, specials, etc., all complete |  |  | 1 No. ( One Number )
29 | 68.2.1 |  | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable in surface run of PVC rigid conduit pipe heavy duty with ISI mark with suitable size PVC box (Fire retardent box) of required thickness concealed and covered with 3mm thick laminated hylem sheet for 5 Amps 5 pin plug socket point at convenient places including circuit mains, cost of all materials, specials, etc., all complete (Open Wiring) |  |  | 1 No. ( One Number )
30 | 69.2 |  | Supplying and fixing 15amps 3 pin plug type socket on a suitable size PVC box (Fire retardent box) of required thickness concealed and covered with 3 mm thick laminated hylem sheet inclusive of all connections and cost of all materials. |  |  | 1 No. (One Number)
31 | 70.5.2 |  | Supply and fixing of 4' long 18 W Crystal Glass LED tube Light with ISI mark including cost of all materials twincore flex wire, TW round block and labour charges for fixing in position etc all complete and as directed by the departmental officers (The material should be got approved from the Executive Engineer before use) |  |  | 1 No. (One Number)
32 | 71.3.2 |  | Supply and fixing of 32A DP switch of 500V with metal clad with fuse and neutral (side handle) on suitable TW board with earth connection etc., all complete as directed by the departmental officers. (The quality should be got approved by the Executive Engineer before use). |  |  | 1 No. (One Number)
33 | 75.2 |  | Supply and delivery of following Electric Ceiling fan with ISI mark with blades and double ball bearing, capacitor,etc., complete with 300mm down rod, canopies, capacitor, shackleblades with dimmer electronic regulator suitable for operation on 230 volts 50 HTZ single phase AC supply conforming to ISS No.374/79 and provided with insulation . (The brand should be got approved from the Executive Engineer before supply made). a) 48" Electric fan 1200mm sweep |  |  | 1 No. (One Number)
34 | 77.7.1 |  | Run off main with 2 wires of 2.5 sq.mm. PVC insulated single core multistrand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1 kv grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS:694/1990,1.1. k.v. grade cable in surface run of 19mm/20mm dia rigid PVC conduit pipe heavy duty with ISI mark cost of all materials, specials etc., all complete. (Open wiring) |  |  | 1 RMT (One Running Metre)
35 | 84.3.1 |  | Run off main with 2 wires of 4 sq.mm. PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1 kv grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1. k.v. grade cable in Surface run of 19mm/20mm dia rigid PVC conduit pipe heavy duty with ISI mark cost of all materials, specials etc., all complete. (Open wiring) |  |  | 1 Rmt (One Running Metre
36 | 176.3.1 |  | Supplying and fixing of 8 way single phase and neutral MCB sheet steel enclosure distribution board with SPMCB DB with metal Door Cover with IP42 Protection and with 1 no 6A to 32A DP 10KA MCB type as incoming and 6 nos 6A to 32A, 10KA SP MCB as outgoing in flush with wall and making good of the concealed portion with earth connection. The MCB DB and MCB's should be with ISI mark (like standard make) including wall cutting, grouting, flushing etc., all complete and as directed by the departmental officers. |  |  | 1 No (One Number)
37 | 178 |  | Earthing Station using Pipe electrode as per ISI specification using 2.1 m of 40 mm dia and 0.15 m of 19 mm dia B Class. GI pipe including earthwork excavation, brickwork in cement mortar, plastering, 38 mm RCC cover for the brick masonry, 19 mm GI Check nuts, bolts, Reducer 40 x 20mm, funnel with wire mesh of 12.5 mm dia, copper plate 125 mm x 50 mm x 6 mm ( 0.36 kg ), including 1 bag ( 40 kgs ) charcoal, salt 10 kg including cost of all materials and labour,etc all complete as per relevant standard specification and as directed by the departmental officers. |  |  | 1 No. ( One Number )
38 | 207.3.6 |  | Painting the old walls with two coats of 1st class ready mixed plastic emulsion paint of best approved quality colour and shade clean removal of dirt and dust etc., complete including cost of necessary brushes, labour charges, putty etc., complying with relevant standard specification. (The paint should be supplied by the contractors at his own cost.The quality and shade of the paint should be got approved by the Executive Engineer before use.) (Excluding scrapping) |  |  | 1m2 (One Square metre)
39 | 207.3.9 |  | Painting one coat with ready mixed plastic emulsion paint primer for old wall of first class quality paint of approved colour and shade including thorough scrapping the old surface, clean removal of dirt and dust etc complete including cost of necessary brushes, labour charges, patty etc complying with relevant standard specification. The paint should be supplied by the contractors at his own cost. |  |  | 1m2 (One Square metre)
40 | 207.4 |  | Painting the old wood work with two coats of approved Ist class synthetic enamel paint including thorough scrapping the old paint using sand paper as required by the departmental officers including cost of material, labour for painting, supplying etc., all complete as directed by the departmental officers. (The paint quantity and shade should be got approved by Executive Engineer before using.) |  |  | 1m2 (One Square metre)
41 | 209.7 |  | Clean removal of the existing damaged floor and wall plastering without damaged existing structure and cleaning the surface thoroughly in order to remove all deleterious using steel matters, oil,grease,wire brushes and applying two coats of fosroc brush bond waterproofing with one layer of 45GSM fibre mesh for entire flooring and providing all-round the walls 20cm height including cost of materials,labour charges etc., all complete as directed by the departmental officers. |  |  | 1m2 (One Square metre)
42 | 222.2.1 |  | Labour charges for the removing and refixing the damaged door shutter or other similar joinery works including frames, hinges, fastenings and shutters from the existing structure and stacking the same carefully for reuse if any in the departmental stores at site of work and as directed by the departmental officers etc., all complete (including removing the furniture fittings such as hinges, hookes and eyes etc.,) |  |  | 1m2 (One Square metre)
43 | 222.2.2 |  | Labour charges for the removing and refixing the damaged window shutter or other similar joinery works including frames, hinges, fastenings and shutters from the existing structure and stacking the same carefully for reuse if any in the departmental stores at site of work and as directed by the departmental officers etc., all complete (including removing the furniture fittings such as hinges, hookes and eyes etc.,) |  |  | 1m2 (One Square metre)
44 | 362.2.2 |  | Supplying and fixing of Stain free Nano polish Vitrified Tiles of size (600x600x8mm) for flooring and other similar works in cement mortar 1:3 (one of cement and three of crushed stone sand) 20mm thick including fixing in position, cutting the tiles to the required size wherever necessary pointing the joints with grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand and quality of tiles should be got approved from Executive Engineer before use) |  |  | 1m2 (One Square metre)
45 | 379.5.2 |  | Supply and fixing of Jet black Granite slab (superfine polished with machine cut edges) of size 4'-0"x 2'-0" of 18 mm to 20mm thick for platform slabs including super fine polish, finishing and fixing in position and pointing with CM 1:3 (One of cement and three of curshed stone sand) complying with relevant Standard specifications etc., (Measurement will be taken including bearing also) as directed by the departmental officers (Quality of Granite slab shall be got approved by the Executive Engineer before fixing) Ground floor |  |  | 1m2 (One Square metre)
46 | 383.4.3 |  | Supply, delivery and fixing of Stainless steel sink size of 600mm x 450mm x 200mm thick using 32mm dia ‘B’ class G.I. waste water pipe and 32 mm dia C.P. waste coupling (sample should be got approved from the Executive Engineer before use) true to spirit level including finishing neatly, and fixing in position complying with relevant standard specifications etc., complete in all floors. |  |  | 1 No. ( One Number)
47 | 451.3.3 |  | Supplying and fixing of the following water supply fittings of approved make (ISI) and quality including cost and labour charges for fixing etc., all complete and as directed by the departmental officers. (The PVC water supply fittings should be got approved from the EE before fixing) a) 15mm dia CP angle cock |  |  | 1 No. ( One Number)
48 |  |  | b) 15mm dia Stainless Steel Health Faucet |  |  | 1 No. ( One Number)
49 |  |  | c) 15mm dia SS Heavy Duty Long Body Tap |  |  | 1 No. ( One Number)
50 | 741.1.1 |  | Supply and fixing of 20A Double pole plug and sockets in sheet steel enclosure with 32 amps DP MCB in flush with wall, with earth connection (for AC plug) of approved brand including cost of materials and labour charges etc., all complete as directed by the departmental officers. (The brand and quality should be got approved by the Executive Engineer before use). |  |  | 1 No. (One Number)
51 | 753 |  | Construction of Inspection chamber with brickjelly cement concrete 1:8:16 ( One of cement, eight of crushed of stone sand and sixteen of broken brick jelly 40mm gauge 15cm, thick for foundation and 23cm thick brick mansonry in C.M 1:5 using chamber burnt bricks of size 9"x4 1/2"x3" and plastering with CM 1:3 (one of cement, three of crushed stone sand ) 5cm thick precast cover slab excluding the cost and fabrication of reinforcement grills but including benching channelling fixing the cover slab in position curing, finishing etc., complete in all respects. b.Inspection Chamber size 60 x 60 x 60 cm |  |  | 1 No. (One Number)
52 | 832.5.3 |  | Supplying and fixing of UPVC (Un-Plasticized Polyvinyl Chloride) Louvered Ventilators of from the profile the size of outer frame 60mmx58mm and shutter profile size of 60x78mm. Both profiles are reinforced with GI/1mm 125 GSM and 100% corrosion free, the profile are multi chambered sections with wall thickness of 2mm. The EPDM rubber (black colour) covered with all over the edges of frame and shutter. The corners and joints should be welded and cleaned. Radiations pin headed glass 4mm thick should be provided in the louvers. The ventilator should be fixed to the wall with 100% packing with screws and silicon packing all round the frames etc. all complete in all respects as directed by the departmental officers. (The colour, brand and quality should be got approved from the Executive Engineer before use.) |  |  | 1m2 (One Square metre)
53 | 983 |  | Providing and applying charges of Krystal Internal Membrane of Crystalline waterproofing admixture 3.2kg per one cum added in M30 grade reinforced cement concrete including cost of water proofing admixture and labour charge for mixing etc all complete and as directed by the departmental officers. |  |  | 1m3 (One Cubic metre)
54 | 983.1 |  | Providing waterproofing protective for outer wall using with applying two coats of fosroc brush bond water proofing admixture over the existing walls and plastering with CM 1:2 (One of cement and two of crushed stone sand), 20mm thick mixed with fosroc WL waterproofing admixture for alround the outer wall to prevent water seepage from walls including cost of materials labour charges etc all complete and as directed by the departmental officers |  |  | 1m2 (One Square metre)

## CS (2)
Sl. No. | ITEM No. | QTY | DESCRIPTION | TNBP NO | Rate | UNIT | Amount
1 | 1.1 | 24.5 | Earth work excavation for foundation in all soils and sub-soils to the required depth as may be directed except in hard rock requiring blasting but inclusive of shoring, strutting, and bailing out water wherever necessary and refilling the sides of foundation with excavated earth in 150mm thick layers well watered rammed and consolidated and depositing the surplus earth in places shown clearing and levelling the site with an initial lead of 10 metres and lift as specified here under etc. complete in all respects complying with relevant standard specifications. (Including Refilling). a) 0 to 2m depth. | 17, 23 & 24 | 250 | 1m3 (One Cubic metre) | 6125 | 247.31 | 6059.095 | 250 | 6125 | 300 | 7350
2 | 15.1 | 4.6 | Providing Cuddappah slab of 20mm thick, finishing with two sides for cupboard, ward-robes, shelves, kitchen platform slabs, sink and other similar works including finishing and fixing in position complying with relevant Standard specifications etc., complete in the following floors (Measurement will be taken including bearing also) as directed by the departmental officers (Quality of Cuddappah slab shall be got approved by the Executive Engineer before fixing. I. 20mm thick In Ground Floor |  | 560 | 1m2 (One Square metre) | 2576 | 563.35 | 2591.41 | 560 | 2576 | 750 | 3450
Electrical arrangement
3 | 74 | 7 | Charges for assembling and fixing of ceiling fan of different sweep with necessary connections and fixing of fan regulator on the existing board etc., all complete (Excluding cost of fan) |  | 450 | 1 No. (One Number) | 3150 | 571 | 3997 | 450 | 3150 | 450 | 3150
4 | 76 | 14 | Supplying and laying of 8SWG GI wire on wall below ground levels with necessary ‘U’ Nails, earth work excavation and refilling etc... including cost of all materials etc.. all complete. |  | 25 | 1 Rmt (One Running Metre | 350 | 26 | 364 | 25 | 350 | 30 | 420
5 | 77.4 | 25 | Supplying, laying and concealing of PVC pipe of 20mm dia with necessary specials and other materials including Run off 1No. Fish wire (G.I.22g) for drawing cable for T.V./Telephone etc., all complete and as directed by the departmental officers. |  | 100 | 1 Rmt (One Running Metre | 2500 | 87.66 | 2191.5 | 100 | 2500 | 120 | 3000
6 | 112 | 2 | Supplying and fixing of 300 mm dia sweep AC exhaust fan of approved ISI quality including necessary wall opening, fixing and finishing the wall opening and making good including cost of material, labour for fixing, chipping and redoing necessary inter connection, scaffolding, hire charges for tools and plants etc., all complete and as directed by the departmental officers. |  | 2300 | 1 No. (One Number) | 4600 | 2336 | 4672 | 2300 | 4600 | 2500 | 5000
7 | 238 | 0.525 | Applying one coat of anticorrosive treatment on steel reinforcement rods (20 ltrs. of anitcorrosive chemical for one mertic tonne of steel reinforcement rods) at site including a cost of required quantity of anticorrosive chemicals, (best approved quality) cement, consumables such as brushes, gloves and labour for anticorrosive coating etc. complete and as directed by the departmental officers. (The Quality and brand of anticorrosive chemaical should be got approved by the Executive Engineer before use). |  | 3000 | 1 MT (One Metric Tonne) | 1575 | 4755.5 | 2496.6375 | 3000 | 1575 | 4500 | 2362.5
ANNEXURE
8 | 3.1.3 | 10.5 | Plain cement concrete 1:5:10 (One of cement, five of crushed stone sand and ten of hard broken stone Jelly) for foundation using 40 mm gauge hard broken stone jelly inclusive of shoring, strutting and bailing out water wherever necessary ramming, curing etc., complete in all respects complying with relevant standard specifications and as directed by the departmental officers. |  | 4700 | 1m3 (One Cubic metre) | 49350 | 4902.14 | 51472.47 | 4900 | 51450 | 4500 | 47250
9 | 8.2.3.1 | 10.5 | Providing and laying in position, Standardised Concrete Mix M-30 Grade in accordance with IS:456-2000 using 20mm and down graded hard broken granite stone jelly for the all RCC items of works with minimum cement content of 400 Kg/m3 and maximum water cement ratio of 0.45, including admixture (plasticiser/super plasticiser) in recommended proportions as per IS:9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability with about (5.0 cum) 7730Kg of 20mm machine crushed stone jelly and with about (3.3 cum) 5156 Kg of 10-12mm machine crushed stone jelly and with about (4.79 cum) 7670Kg of crushed stone sand (for making 10 cum) but excluding cost of reinforcement grill and fabricating charges, centering and shuttering and also including laying, vibrating with mechanical vibrators, finishing, curing etc., and providing fixtures like fan clamps in the RCC floor/roof slabs wherever necessary without claiming extra etc., complete complying with relevent standard specification and as directed by the departmental officers. The coarse and fine aggregates to be used should comply with requirements of IS standards. (No separate payment will be made by the Departmental for the excess usage of materials) b. In Ground floor |  | 8400 | 1m3 (One Cubic metre) | 88200 | 8720.53 | 91565.565 | 8700 | 91350 | 9000 | 94500
10 | 10.2.2 | 5 | Brick partition wall in Cement Mortar 1:4 (One of cement and four of crushed stone sand,) 114mm thick for super structure in the following floors using chamber burnt bricks of size 9”x4½"x3” (23x11.4x7.5cm) including labour for fixing the doors, windows and ventilator frames in position, fixing of hold fasts, scaffoldings, curing etc., complete in all respect complying with relevant standard specifications and drawings b) In Ground floor |  | 900 | 1m2 (One Square metre) | 4500 | 866.58 | 4332.9 | 900 | 4500 | 1000 | 5000
11 | 21.5.2.2 | 3 | Providing and fixing factory made unplasticized polyvinyl chloride (UPVC) Door Frame of size 50X47mm with a wall thickness of 5mm, made out extruded 5mm rigid UPVC foam sheet, mitred at two corners and joined with 2 nos of 150mm long brackets of 15X15mm M.S square tube. The two vertical and horizontal door profiles are to be reinforced with 19X19mm M.S Square tube of 19 gauge with primer coat. The door frame shall be fixed to the wall using 65/100mm long M.S screw through the frame by using PVC fasteners. A minimum of 4 nos screws to be provided for each vertical member & minimum 2 nos for horizontal member etc., and providing and fixing 30mm thick factory made door shutter with unplasticized polyvinyl chloride (UPVC) solid panel foam sheet , structured with M.S. tube of 19 gauge thickness and size 19 x 19mm for styles & 15mm x 15mm for top & bottom rails. Panelling of 5mm thick UPVC One Side Printed Lamination single sheet to be fitted in the M.S. frame welded / sealed to the styles and rails covered with 5mm thick heat moulded UPVC "C" channel of 30 x 50mm and 5mm thick, 75mm wide UPVC sheet for top rail, lock rail and bottom rail on either side and 10mm (5mm X 2 Nos) thick, 20mm wide cross UPVC sheet as gap insert for top rail & bottom rail and joined together with PVC solvent cement adhesive. An additional 5mm thick UPVC strip of 20mm width is to be stuck on the interior side of the 'C' Channel using PVC solvent cement adhesive including cost and labour charges for fixing of 3 nos 4” SS butt hinges and Aluminium furniture fittings such as 1 No 4" Tower bolt, 1 No 5" Aldrop, 2 Nos 6" flat 'D' type Handle etc are included the fitting provided shall bear ISI marks. (The quality and brand of door shutter and furniture fittings should be got approved from the Executive Engineer before use) |  | 3300 | 1m2 (One Square metre) | 9900 | 3325 | 9975 | 3300 | 9900 | 4000 | 12000
12 | 22.5.1 | 54 | Supplying and fixing of following furniture fittings of approved make ISI including cost of materials and labour charges for fixing etc., all complete as directed by the departemntal officers. (The furniture fittings should be got approved from the Executive Engineer before use) a) Butt Hinges with Nylon Washers of 75mm x 30mm (with required screws) |  | 60 | 1 No. (One Number) | 3240 | 64.5 | 3483 | 60 | 3240 | 60 | 3240
13 |  | 18 | b) Tower Bolts of 150mm long and 12mm dia (with required screws) |  | 80 | 1 No. (One Number) | 1440 | 84.5 | 1521 | 80 | 1440 | 80 | 1440
14 |  | 54 | c) Handles "D" type of 100mm long with required screws |  | 50 | 1 No. (One Number) | 2700 | 46 | 2484 | 50 | 2700 | 50 | 2700
15 |  | 18 | d) Aluminium Door Stopper with Rubber Bush with required screws |  | 70 | 1 No. (One Number) | 1260 | 74 | 1332 | 70 | 1260 | 70 | 1260
16 |  | 9 | e) Aldrops of 250mm long and 16mm dia with required screws, bolts and nuts |  | 240 | 1 No. (One Number) | 2160 | 235.5 | 2119.5 | 240 | 2160 | 300 | 2700
17 | 29.9.4.1 | 4.2 | Supplying and laying of Colour matt finish floor Tiles of size 305x305mm (12"x12") for flooring and other similar works (Best approved superior quality and the same shall be got approved from the Executive Engineer before using) over cement mortor 1:3 (One of cement and three of crushed stone sand) 20mm thick including fixing in position, cutting the tiles to the required size wherever necessary pointing the joints with Grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand quality of tiles should be got approved from Executive Engineer before use). |  | 1400 | 1m2 (One Square metre) | 5880 | 1403.2 | 5893.44 | 1400 | 5880 | 1300 | 5460
18 | 29.9.5.1 | 23 | Supplying and fixing of Colour matt finish Wall Tiles of size 12"x18" for wall and other similar works (Best approved superior quality and the same shall be got approved from the Executive Engineer before using) over cement plastering in CM 1:2 (One of cement and two of crushed stone sand) 10mm thick including fixing in position, cutting the tiles to the required size wherever necessary, pointing the joints with Grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand quality of tiles should be got approved from Executive Engineer before use ). |  | 1600 | 1m2 (One Square metre) | 36800 | 1699.98 | 39099.54 | 1600 | 36800 | 1800 | 41400
19 | 33.2.1 | 8.5 | Plastering with CM 1:5 (One of cement and five of crushed stone sand) 12mm thick finished with neat cement including plasticizer, providing band cornice, ceiling cornice, curing, scaffolding, etc., complete in all respects and complying with relevant standard specifications. |  | 260 | 1m2 (One Square metre) | 2210 | 261.5 | 2222.75 | 260 | 2210 | 260 | 2210
20 | 43.2.1 | 0.525 | Supplying, fabricating and placing in position of Mild steel Grills / Ribbed Tor Steels (without cement slurry) of all diameters for reinforcement for all floors including cost of binding wire insulated with PVC, bending tying etc., all complete and as directed by the departmental officers. |  | 87500 | 1 MT (One Metric Tonne) | 45937.5 | 90322.8 | 47419.47 | 90000 | 47250 | 100000 | 52500
21 | 52.1.1 | 12 | Supplying, laying, fixing and jointing the following PVC pipes as per ASTM D - 1785 of schedule 40 of wall thickness not less than the specified in IS 4985 suitable for plumbing by threading of wall thickness including the cost of suitable UPVC specials like Elbow, Tee reducers, Plug, unions, bend, coupler, nipple/ UPVC gate valve, UPVC check and UPVC / ball valve etc., wherever required above the ground level including the cost of teflon tape, PVC special clamps, nails, etc., fixing on wall to the proper gradient and alignment and redoing the chipped of masonry etc., as directed by the departmental officers. (The brand and quality of pipes and specials should be got approved by the EE/SE/CE before use in works) c) 20mm dia ASTM D schedule 40 threaded PVC pipe with necessary UPVC specials |  | 235 | 1 Rmt (One Running Metre | 2820 | 238.64 | 2863.68 | 235 | 2820 | 240 | 2880
22 | 57.1.2 | 1 | Supplying and fixing EWC superior variety (Colour) 500mm with PVC SWR grade 'P' or 'S' trap including cost and fixing of double flapped coloured plastic sheet cover PVC flushing cistern in appropriate level as directed by the departmental officers at a maximum level of 5’6” and of approved brand of 10litres capacity including fittings such as CI brackets. PVC connection GM wheel valve, Hex nipple, etc., complete (The Quality and brand of EWC and plastic cover shall be got approved from the Executive Engineer before fixing) |  | 7650 | 1 No. (One Number) | 7650 | 7651.85 | 7651.85 | 7650 | 7650 | 8000 | 8000
23 | 58.3 | 10 | Supplying and fixing the following dia PVC (SWR) pipe with ISI mark confirming to IS 13952:1992- type 'B' for soil line with relevant specials confirming to IS 14735 including jointing with seal ring confirming to IS 5382 with leaving a gap about 10mm to allow thermal expansion,fixing the pipes into walls with necessary wooden plug, screws, holding wherever necessary and making good of the dismantled portion with necessary connections to sanitary fittings etc., complete in all respects and as directed by the departmental officers. a) 110mm dia PVC SWR pipe including all required PVC specials etc., all complete., |  | 750 | 1 Rmt (One Running Metre | 7500 | 735.27 | 7352.7 | 750 | 7500 | 700 | 7000
24 |  | 12 | b) 75mm dia PVC SWR pipe including all required PVC specials etc., all complete., |  | 610 | 1 Rmt (One Running Metre | 7320 | 617.97 | 7415.64 | 610 | 7320 | 600 | 7200
25 | 60.1 | 5 | Supplying and fixing of PVC Nahani Trap not less than 75mm 4 way / 2 way (Superior variety) having minimum of water seal of 50mm confirm to relevant I.S. specifications with its latest amendments including resting on the bed of brick jelly concrete 1:5:10 (One of cement, five of crushed stone sand and ten of 40 mm gauge brick jelly) etc., complete as directed by the departmental officers (The PVC Nahani Trap should be got approved from the Executive Engineer before use) | 102 | 160 | 1 No. (One Number) | 800 | 160 | 800 | 160 | 800 | 160 | 800
26 | 61.3 | 18 | Supplying, laying and jointing the following dia UPVC Non Pressure pipe of SN8 SDR 34 (S 16.5) as per IS 15328/2003, superior variety and tested with water, including necessary earth work excavation for trenches and refilling the same, well rammed and consolidated after the pipes are jointed and laid to proper gradiant to the alignment as directed by the departmental officers. (SN8 SDR 34 (S16.5), as per IS 15328/2003, should be got approved by the EE/SE/CE before use in works) a. 160 mm UPVC Non Pressure pipe |  | 1000 | 1 Rmt (One Running Metre | 18000 | 815.71 | 14682.78 | 1000 | 18000 | 1000 | 18000
27 | 64.1.1 | 21 | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark conforming to IS: 694/1990, 1.1K.v. grade cable with continuous earth by means of 1.5sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark conforming to IS: 694/1990, 1.1 k.v . grade cable in surface run of PVC rigid conduit pipe heavy duty with ISI mark with suitable size TW switch box required thickness concealed and covered with 3 mm thick laminated hylem sheet controlled by 5Amps flush type switch including circuit mains cost of all materials, specials etc., all complete.(Open wiring) a. Light point with ceiling rose |  | 900 | 1 No. (One Number) | 18900 | 895 | 18795 | 900 | 18900 | 1000 | 21000
28 | 67.1 | 7 | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable with continuous earth by means of 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cablewith ISI mark confirming to IS: 694/1990,1.1.k.v. grade cable in fully concealed PVC rigid conduit pipe heavy duty with ISI mark with suitable size MS box of 16g thick concealed and covered with 3mm thick laminated hylem sheet for 5 amps 5 pin plug socket point at Switch Board Itself including circuit mains, cost of all materials, specials, etc., all complete |  | 830 | 1 No. (One Number) | 5810 | 830 | 5810 | 830 | 5810 | 830 | 5810
29 | 68.2.1 | 14 | Wiring with 1.5 sqmm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990, 1.1.k.v. grade cable in surface run of PVC rigid conduit pipe heavy duty with ISI mark with suitable size PVC box (Fire retardent box) of required thickness concealed and covered with 3mm thick laminated hylem sheet for 5 Amps 5 pin plug socket point at convenient places including circuit mains, cost of all materials, specials, etc., all complete (Open Wiring) |  | 700 | 1 No. (One Number) | 9800 | 677 | 9478 | 700 | 9800 | 675 | 9450
30 | 69.2 | 9 | Supplying and fixing 15amps 3 pin plug type socket on a suitable size PVC box (Fire retardent box) of required thickness concealed and covered with 3 mm thick laminated hylem sheet inclusive of all connections and cost of all materials. |  | 130 | 1 No. (One Number) | 1170 | 135 | 1215 | 130 | 1170 | 130 | 1170
31 | 70.5.2 | 15 | Supply and fixing of 4' long 18 W Crystal Glass LED tube Light with ISI mark including cost of all materials twincore flex wire, TW round block and labour charges for fixing in position etc all complete and as directed by the departmental officers (The material should be got approved from the Executive Engineer before use) |  | 690 | 1 No. (One Number) | 10350 | 690 | 10350 | 690 | 10350 | 690 | 10350
32 | 71.3.2 | 1 | Supply and fixing of 32A DP switch of 500V with metal clad with fuse and neutral (side handle) on suitable TW board with earth connection etc., all complete as directed by the departmental officers. (The quality should be got approved by the Executive Engineer before use). |  | 1390 | 1 No. (One Number) | 1390 | 1390 | 1390 | 1390 | 1390 | 1390 | 1390
33 | 75.2 | 7 | Supply and delivery of following Electric Ceiling fan with ISI mark with blades and double ball bearing, capacitor,etc., complete with 300mm down rod, canopies, capacitor, shackleblades with dimmer electronic regulator suitable for operation on 230 volts 50 HTZ single phase AC supply conforming to ISS No.374/79 and provided with insulation . (The brand should be got approved from the Executive Engineer before supply made). a) 48" Electric fan 1200mm sweep |  | 1550 | 1 No. (One Number) | 10850 | 1553 | 10871 | 1550 | 10850 | 1550 | 10850
34 | 77.7.1 | 80 | Run off main with 2 wires of 2.5 sq.mm. PVC insulated single core multistrand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1 kv grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS:694/1990,1.1. k.v. grade cable in surface run of 19mm/20mm dia rigid PVC conduit pipe heavy duty with ISI mark cost of all materials, specials etc., all complete. (Open wiring) |  | 150 | 1 Rmt (One Running Metre | 12000 | 146.6 | 11728 | 150 | 12000 | 150 | 12000
35 | 84.3.1 | 129 | Run off main with 2 wires of 4 sq.mm. PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1 kv grade cable with continuous earth by means of 1.5 sq.mm PVC insulated single core multi strand fire retardant flexible copper cable with ISI mark confirming to IS: 694/1990,1.1. k.v. grade cable in Surface run of 19mm/20mm dia rigid PVC conduit pipe heavy duty with ISI mark cost of all materials, specials etc., all complete. (Open wiring) |  | 175 | 1 Rmt (One Running Metre | 22575 | 177 | 22833 | 177 | 22833 | 177 | 22833
36 | 176.3.1 | 1 | Supplying and fixing of 8 way single phase and neutral MCB sheet steel enclosure distribution board with SPMCB DB with metal Door Cover with IP42 Protection and with 1 no 6A to 32A DP 10KA MCB type as incoming and 6 nos 6A to 32A, 10KA SP MCB as outgoing in flush with wall and making good of the concealed portion with earth connection. The MCB DB and MCB's should be with ISI mark (like standard make) including wall cutting, grouting, flushing etc., all complete and as directed by the departmental officers. |  | 3190 | 1 No. (One Number) | 3190 | 3191 | 3191 | 3190 | 3190 | 3190 | 3190
37 | 178 | 1 | Earthing Station using Pipe electrode as per ISI specification using 2.1 m of 40 mm dia and 0.15 m of 19 mm dia B Class. GI pipe including earthwork excavation, brickwork in cement mortar, plastering, 38 mm RCC cover for the brick masonry, 19 mm GI Check nuts, bolts, Reducer 40 x 20mm, funnel with wire mesh of 12.5 mm dia, copper plate 125 mm x 50 mm x 6 mm ( 0.36 kg ), including 1 bag ( 40 kgs ) charcoal, salt 10 kg including cost of all materials and labour,etc all complete as per relevant standard specification and as directed by the departmental officers. |  | 2700 | 1 No. (One Number) | 2700 | 2703 | 2703 | 2700 | 2700 | 2700 | 2700
38 | 207.3.6 | 463 | Painting the old walls with two coats of 1st class ready mixed plastic emulsion paint of best approved quality colour and shade clean removal of dirt and dust etc., complete including cost of necessary brushes, labour charges, putty etc., complying with relevant standard specification. (The paint should be supplied by the contractors at his own cost.The quality and shade of the paint should be got approved by the Executive Engineer before use.) (Excluding scrapping) |  | 165 | 1m2 (One Square metre) | 76395 | 167 | 77321 | 165 | 76395 | 165 | 76395
39 | 207.3.9 | 463 | Painting one coat with ready mixed plastic emulsion paint primer for old wall of first class quality paint of approved colour and shade including thorough scrapping the old surface, clean removal of dirt and dust etc complete including cost of necessary brushes, labour charges, patty etc complying with relevant standard specification. The paint should be supplied by the contractors at his own cost. |  | 74 | 1m2 (One Square metre) | 34262 | 75 | 34725 | 80 | 37040 | 82 | 37966
40 | 207.4 | 104.1 | Painting the old wood work with two coats of approved Ist class synthetic enamel paint including thorough scrapping the old paint using sand paper as required by the departmental officers including cost of material, labour for painting, supplying etc., all complete as directed by the departmental officers. (The paint quantity and shade should be got approved by Executive Engineer before using.) |  | 165 | 1m2 (One Square metre) | 17176.5 | 164 | 17072.4 | 165 | 17176.5 | 165 | 17176.5
41 | 209.7 | 128 | Clean removal of the existing damaged floor and wall plastering without damaged existing structure and cleaning the surface thoroughly in order to remove all deleterious using steel matters, oil,grease,wire brushes and applying two coats of fosroc brush bond waterproofing with one layer of 45GSM fibre mesh for entire flooring and providing all-round the walls 20cm height including cost of materials,labour charges etc., all complete as directed by the departmental officers. |  | 640 | 1m2 (One Square metre) | 81920 | 660 | 84480 | 660 | 84480 | 660 | 84480
42 | 222.2.1 | 24 | Labour charges for the removing and refixing the damaged door shutter or other similar joinery works including frames, hinges, fastenings and shutters from the existing structure and stacking the same carefully for reuse if any in the departmental stores at site of work and as directed by the departmental officers etc., all complete (including removing the furniture fittings such as hinges, hookes and eyes etc.,) |  | 380 | 1m2 (One Square metre) | 9120 | 383.9 | 9213.6 | 380 | 9120 | 380 | 9120
43 | 222.2.2 | 16.2 | Labour charges for the removing and refixing the damaged window shutter or other similar joinery works including frames, hinges, fastenings and shutters from the existing structure and stacking the same carefully for reuse if any in the departmental stores at site of work and as directed by the departmental officers etc., all complete (including removing the furniture fittings such as hinges, hookes and eyes etc.,) |  | 440 | 1m2 (One Square metre) | 7128 | 444.51 | 7201.062 | 440 | 7128 | 440 | 7128
44 | 362.2.2 | 115.5 | Supplying and fixing of Stain free Nano polish Vitrified Tiles of size (600x600x8mm) for flooring and other similar works in cement mortar 1:3 (one of cement and three of crushed stone sand) 20mm thick including fixing in position, cutting the tiles to the required size wherever necessary pointing the joints with grout (Tile joint filler), curing, finishing etc., all complete and as directed by the departmental officers. (The brand and quality of tiles should be got approved from Executive Engineer before use) |  | 1470 | 1m2 (One Square metre) | 169785 | 1522.99 | 175905.345 | 1520 | 175560 | 1520 | 175560
45 | 379.5.2 | 1.4 | Supply and fixing of Jet black Granite slab (superfine polished with machine cut edges) of size 4'-0"x 2'-0" of 18 mm to 20mm thick for platform slabs including super fine polish, finishing and fixing in position and pointing with CM 1:3 (One of cement and three of curshed stone sand) complying with relevant Standard specifications etc., (Measurement will be taken including bearing also) as directed by the departmental officers (Quality of Granite slab shall be got approved by the Executive Engineer before fixing) Ground floor |  | 1960 | 1m2 (One Square metre) | 2744 | 1969.38 | 2757.132 | 1960 | 2744 | 1960 | 2744
46 | 383.4.3 | 1 | Supply, delivery and fixing of Stainless steel sink size of 600mm x 450mm x 200mm thick using 32mm dia ‘B’ class G.I. waste water pipe and 32 mm dia C.P. waste coupling (sample should be got approved from the Executive Engineer before use) true to spirit level including finishing neatly, and fixing in position complying with relevant standard specifications etc., complete in all floors. |  | 7140 | 1 No. (One Number) | 7140 | 7140 | 7140 | 7140 | 7140 | 7140 | 7140
47 | 451.3.3 | 2 | Supplying and fixing of the following water supply fittings of approved make (ISI) and quality including cost and labour charges for fixing etc., all complete and as directed by the departmental officers. (The PVC water supply fittings should be got approved from the EE before fixing) a) 15mm dia CP angle cock |  | 1000 | 1 No. (One Number) | 2000 | 1002 | 2004 | 1000 | 2000 | 1000 | 2000
48 |  | 1 | b) 15mm dia Stainless Steel Health Faucet |  | 1375 | 1 No. (One Number) | 1375 | 1375 | 1375 | 1375 | 1375 | 1375 | 1375
49 |  | 2 | c) 15mm dia SS Heavy Duty Long Body Tap |  | 1770 | 1 No. (One Number) | 3540 | 1771 | 3542 | 1770 | 3540 | 1770 | 3540
50 | 741.1.1 | 2 | Supply and fixing of 20A Double pole plug and sockets in sheet steel enclosure with 32 amps DP MCB in flush with wall, with earth connection (for AC plug) of approved brand including cost of materials and labour charges etc., all complete as directed by the departmental officers. (The brand and quality should be got approved by the Executive Engineer before use). |  | 1840 | 1 No. (One Number) | 3680 | 1839 | 3678 | 1840 | 3680 | 1840 | 3680
51 | 753 | 2 | Construction of Inspection chamber with brickjelly cement concrete 1:8:16 ( One of cement, eight of crushed of stone sand and sixteen of broken brick jelly 40mm gauge 15cm, thick for foundation and 23cm thick brick mansonry in C.M 1:5 using chamber burnt bricks of size 9"x4 1/2"x3" and plastering with CM 1:3 (one of cement, three of crushed stone sand ) 5cm thick precast cover slab excluding the cost and fabrication of reinforcement grills but including benching channelling fixing the cover slab in position curing, finishing etc., complete in all respects. b.Inspection Chamber size 60 x 60 x 60 cm |  | 6250 | 1 No. (One Number) | 12500 | 6248.08 | 12496.16 | 6250 | 12500 | 6250 | 12500
52 | 832.5.3 | 1.1 | Supplying and fixing of UPVC (Un-Plasticized Polyvinyl Chloride) Louvered Ventilators of from the profile the size of outer frame 60mmx58mm and shutter profile size of 60x78mm. Both profiles are reinforced with GI/1mm 125 GSM and 100% corrosion free, the profile are multi chambered sections with wall thickness of 2mm. The EPDM rubber (black colour) covered with all over the edges of frame and shutter. The corners and joints should be welded and cleaned. Radiations pin headed glass 4mm thick should be provided in the louvers. The ventilator should be fixed to the wall with 100% packing with screws and silicon packing all round the frames etc. all complete in all respects as directed by the departmental officers. (The colour, brand and quality should be got approved from the Executive Engineer before use.) |  | 8100 | 1m2 (One Square metre) | 8910 | 8106 | 8916.6 | 8100 | 8910 | 8100 | 8910
53 | 983 | 10.5 | Providing and applying charges of Krystal Internal Membrane of Crystalline waterproofing admixture 3.2kg per one cum added in M30 grade reinforced cement concrete including cost of water proofing admixture and labour charge for mixing etc all complete and as directed by the departmental officers. |  | 2000 | 1m3 (One Cubic metre) | 21000 | 2080 | 21840 | 2000 | 21000 | 2000 | 21000
54 | 983.1 | 41 | Providing waterproofing protective for outer wall using with applying two coats of fosroc brush bond water proofing admixture over the existing walls and plastering with CM 1:2 (One of cement and two of crushed stone sand), 20mm thick mixed with fosroc WL waterproofing admixture for alround the outer wall to prevent water seepage from walls including cost of materials labour charges etc all complete and as directed by the departmental officers |  | 1150 | 1m2 (One Square metre) | 47150 | 1170 | 47970 | 1170 | 47970 | 1170 | 47970
[6 empty] | TOTAL | 923104 |  | 942060.2265 |  | 941857.5 |  | 959700
[6 empty] | GST @ 18% | 166158.72 |  | 169570.8408 |  | 169534.35 |  | 172746
[6 empty] | TOTAL | 1089262.72 |  | 1111631.0673 |  | 1111391.85 |  | 1132446