## Abs
Name of work : Additional Interior works for Doors,Toughened Glass andWall putty for the work of special repair works for central co operative bank building at Vannarapettai in Tirunelveli district.
ABSTRACT
SL.No | Description of work | Qty | Units | Rate | Amount
1 | One coat of wall putty incluidng labour charges and materials etc all complete | 1653.65 | M2 | 99.18 | 164009.007
Data
2 | Painting two coats of Interior Emulsion paint including labour charges and materials etc all complete | 903.9 | M2 | 240.2 | 217116.78
Data
3 | Supply and fixing of calcium silicate board panelling with required spacing horizondaly and verticaly 25 x 50 mm channels using and fixed with necessary screws and joint filt with sealant of dow corning 789 or equialant sealant and the required area as directed by departmental officers the rate inclusive of all materials ,labour ,power and conveniyence of materilas to the work site loading and unloading etc | 96.4 | M2 | 1614 | 155589.6
Quotation
4 | Supply and fixing of Flush door size ( 1200 x 2400 mm ) single leaf including labours and materials etc all complete. | 2.7 | M2 | 2866.16 | 7738.632
Data
5 | Supply and fixing of Flush door size ( 900 x 2400 mm ) single leaf including labours and materials etc all complete. | 2.05 | M2 | 3059.74 | 6272.467
Data
6 | Supply and fixing of Teak wood Glass door size (1500 x 2400 mm ) Double leaf including labours and materials etc all complete. | 3.05 | M2 | 5494.4674 | 16758.1255
Observed data
7 | Supply and fixing of TW Wrought and put up including labour charges etc all complete
a) | T.W.SCANTLING 2M-3M LONG | 0.01 | M3 | 125974.5 | 1259.745
Data
b) | T.W.SCANTLING UP TO 2M LONG | 0.08175 | M3 | 113774.5 | 9301.0654
Data
8 | Supply and fixing of Aluminium Hydralic door closer including materials and labour charges etc all complete | 4 | No | 1008 | 4032
SR P/44 23-24
9 | Supply and installation of 4 KVA capacity automatic voltage Stablizer with time delay relay etc all complete | 12 | No | 4441 | 53292
SR P/153 23-24
10 | Supply and installation of 5 KVA capacity automatic voltage Stablizer with time delay relay etc all complete | 1 | No | 4940 | 4940
SR P/154 23-24
11 | Supply and fixing of Galvanium sheet 0.47 mm thick etc all complete | 19.5 | M2 | 1023.09 | 19950.255
Data
12 | Supplying and fixing in position of UPVC Ventilator louvered ventilator type for all sizes etc all complete | 2.9 | M2 | 8106 | 23507.4
SR P/70 23-24
13 | Supplying and fixing in position of UPVC window of casement type( open) for all sizes etc all complete | 4.1 | M2 | 7482 | 30676.2
SR P/71 23-24
14 | Supply and fixing of Healthfauct hose including materials etc all complete | 22 | No | 1013 | 22286
SR P/62 23-24
15 | Supplying and fixing the wall Panelling fixing the water proof plywood 9mm thick board over the country wood planks. Over the plywood OST sheet of 4mm thick will be fixed with necessary screws and fevicol giving neat finish etc all complete | 22.5 | M2 | 4672.75 | 105136.875
Data
16 | Supply and fixing of 12 mm thick Toughened Glass door with including handle ,hinges,lock,base pinplate all materials and tools ,Transportation charges etc all complete | 5.05 | M2 | 6456 | 32602.8
Quotation
17 | Providing wooden MELAMEN DOOR POLISH for new door including labour charges etc all complete | 27.55 | M2 | 1489.69 | 41040.9595
Data
18 | Supply and fixing of ms rectanular square pipe size 70x30x2.9 mm etc all complete | 129.8 | Kg | 70.15 | 9105.47
Data
19 | Labour charges for truss iron works etc all complete | 129.8 | Kg | 55.35 | 7184.43
SR P/29 23-24
| Total |  |  |  | 931799.8114
| GST @ 18% |  |  |  | 167723.9661
| Grand Total |  |  |  | 1099523.7775
| Labour welfare fund 1 % |  |  |  | 9317.9981
| Supervision charges 7.5 % |  |  |  | 69884.9859
| Supervision charges Gst 18% |  |  |  | 12579.2975
| Total |  |  |  | 1191306.0589
|  |  | Say | = | 11.914 Lakhs

## Detail
Name of work :Additional Interior works for Door,Cupboard shutter,Wall putty for the work of special repair works for central co operative bank building at Vannarapettai in Tirunelveli district.
DETAIL ESTIMATE
SL.No | Description of work | Nos |  |  | L | B | D | QTY
1 | One coat of wall putty incluidng labour charges and materials etc all complete
| Bank s/c inner alround | 1 | x | 1 | 20.6 |  | 12.5 | 257.5
| D/f H/R door | -1 | x | 1 | 1 |  | 2.1 | -2.1
| D/f H/R window | -1 | x | 1 | 2.5 |  | 1.65 | -4.125
| D/f H/R landing slab | -1 | x | 1 | 9 |  | 0.26 | -2.34
| D/f H/R landing slab | -1 | x | 1 | 4.5 |  | 1.5 | -6.75
| Add pillar both side | 1 | x | 2 | 1.5 |  | 1.5 | 4.5
| D/f s/c window | -1 | x | 4 | 3 |  | 0.96 | -11.52
| D/f mid landing | -1 | x | 1 | 9 |  | 0.26 | -2.34
| D/f SF window | -1 | x | 1 | 2.5 |  | 1.65 | -4.125
| D/f SF Landing | -1 | x | 1 | 6 |  | 0.26 | -1.56
| D/f SF open | -1 | x | 1 | 2.5 |  | 3 | -7.5
| D/f FF Midlanding | -1 | x | 1 | 9 |  | 0.26 | -2.34
| D/f FF Window | -1 | x | 1 | 2.5 |  | 1.65 | -4.125
| D/f FF open | -1 | x | 1 | 4 |  | 3 | -12
| D/f GF midlanding | -1 | x | 1 | 6 |  | 0.26 | -1.56
| D/f GF open | -1 | x | 1 | 4 |  | 3 | -12
| D/f GF open | -1 | x | 1 | 2.5 |  | 2 | -5
| Add s/c window jams | 1 | x | 3 | 8.3 | 0.08 |  | 1.992
| Add s/c window jams | 1 | x | 4 | 14 | 0.08 |  | 4.48
| Open jams | 1 | x | 2 | 11 | 0.55 |  | 12.1
| GF Reception inner alround | 1 | x | 1 | 24 |  | 3.3 | 79.2
| D/f Open | -1 | x | 1 | 4 |  | 3 | -12
| D/f Window | -1 | x | 1 | 0.95 |  | 1.65 | -1.5675
| D/f Lift area | -1 | x | 1 | 1.75 |  | 2.55 | -4.4625
| FF Reception inner alround | 1 | x | 1 | 24 |  | 3 | 72
| D/f open | -1 | x | 1 | 4 |  | 3 | -12
| D/f Lift area | -1 | x | 1 | 1.75 |  | 2.55 | -4.4625
| D/f Door | -1 | x | 1 | 0.95 |  | 1.75 | -1.6625
| D/f Partion area | -1 | x | 1 | 5.55 |  | 3 | -16.65
| D/f Door | -1 | x | 2 | 1.45 |  | 2.25 | -6.525
| FF PC Near room inner alround | 1 | x | 1 | 12.85 |  | 2.93 | 37.6505
| D/f window | -1 | x | 1 | 1 |  | 0.6 | -0.6
| D/f window | -1 | x | 1 | 1.65 |  | 1.7 | -2.805
| PC Inner alround | 1 | x | 1 | 19.28 |  | 2.9 | 55.912
| D/f Window | -1 | x | 1 | 0.9 |  | 1.1 | -0.99
| D/f Door | -1 | x | 1 | 1.3 |  | 2.35 | -3.055
| D/f Door | -1 | x | 1 | 1.2 |  | 2.24 | -2.688
| D/f Pillar | -1 | x | 1 | 0.85 |  | 2.9 | -2.465
| MD Rest inner alround | 1 | x | 1 | 19.98 |  | 2.9 | 57.942
| D/f Window | -1 | x | 1 | 1.7 |  | 1.7 | -2.89
| D/f Toilet door | -1 | x | 1 | 0.75 |  | 1.9 | -1.425
| D/f Door | -1 | x | 1 | 0.9 |  | 2.25 | -2.025
| MD Toilet wall alround | 1 | x | 1 | 11.7 |  | 0.45 | 5.265
| FF Entrance lift wall | 1 | x | 1 | 19.1 |  | 2.85 | 54.435
| D/f Door | -1 | x | 2 | 1.45 |  | 2.25 | -6.525
| D/f PC Open | -1 | x | 1 | 1.38 |  | 2.34 | -3.2292
| Dining inner wall | 1 | x | 1 | 1.8 |  | 2.75 | 4.95
| Pillar side | 1 | x | 1 | 0.5 |  | 2.75 | 1.375
| Toilet verandha rear side | 1 | x | 1 | 2.75 |  | 2.7 | 7.425
| D/f Window | -1 | x | 1 | 2.45 |  | 1.7 | -4.165
| Toilet pillar | 1 | x | 1 | 0.85 |  | 3.3 | 2.805
| Toilet passage | 1 | x | 1 | 6.15 |  | 1.25 | 7.6875
| Toilet passage | 1 | x | 1 | 6.15 |  | 0.63 | 3.8745
| Passage side | 1 | x | 2 | 1.5 |  | 0.63 | 1.89
| GM Room pillar | 1 | x | 1 | 2.2 |  | 2.7 | 5.94
| GM Inner rear wall | 1 | x | 1 | 2.85 |  | 2.7 | 7.695
| D/f Window | -1 | x | 1 | 2.45 |  | 1.7 | -4.165
| Toilet alround wall | 1 | x | 1 | 5.55 |  | 2.15 | 11.9325
| D/f TD door | -1 | x | 1 | 0.75 |  | 2.1 | -1.575
| Toilet inner extra | 1 | x | 1 | 1.3 |  | 1.15 | 1.495
| CR Room front wall | 1 | x | 1 | 9 |  | 2.15 | 19.35
| D/f TD door | 1 | x | 1 | 0.75 |  | 2.1 | 1.575
| Toilet wall | 1 | x | 1 | 1.5 |  | 1.15 | 1.725
| Pillar alround | 1 | x | 1 | 2.2 |  | 2.7 | 5.94
| CR East side wall | 1 | x | 1 | 8.76 |  | 2.7 | 23.652
| D/f Window | -1 | x | 3 | 2.45 |  | 1.7 | -12.495
| FF Hall east side wall | 1 | x | 1 | 26.5 |  | 2.7 | 71.55
| D/f Window | -2 | x | 3 | 1.65 |  | 1.65 | -16.335
| Add Window jams | 1 | x | 6 | 6.6 | 0.09 |  | 3.564
| Add Window jams | 1 | x | 3 | 8.3 | 0.09 |  | 2.241
| D/f Window | -1 | x | 2 | 0.6 |  | 1.65 | -1.98
| Add Window jams | 1 | x | 2 | 4.5 | 0.09 |  | 0.81
| Add Window jams | 1 | x | 3 | 8.3 | 0.09 |  | 2.241
| Add s/c window jams | 1 | x | 4 | 7.92 | 0.09 |  | 2.8512
| Add MD window jams | 1 | x | 1 | 6.8 | 0.09 |  | 0.612
| Add Terrace door jams | 1 | x | 1 | 5.4 | 0.09 |  | 0.486
| Gents common toilet inner wall -FF | 1 | x | 2 | 4.2 |  | 1.4 | 11.76
| Gents common Rear side wall -FF | 1 | x | 1 | 2.72 |  | 1 | 2.72
| FF Gents Toilet wall | 1 | x | 1 | 2.72 |  | 1.55 | 4.216
| Add jams | 1 | x | 2 | 1.4 | 0.15 |  | 0.42
| Door top wall | 1 | x | 1 | 2.72 | 0.6 |  | 1.632
| Inbetween wall | 1 | x | 2 | 1.25 |  | 0.6 | 1.5
| FF Ladies toilet wall inner | 1 | x | 2 | 4.2 |  | 1.4 | 11.76
| FF Ladies toilet rear side wall | 1 | x | 1 | 1.95 |  | 1 | 1.95
| FF Ladies front side wall | 1 | x | 1 | 1.95 |  | 0.6 | 1.17
| Gents single toilet wall | 1 | x | 1 | 10.6 |  | 1.4 | 14.84
| Door top wall | 1 | x | 1 | 1.25 |  | 0.6 | 0.75
| GF Gents toilet wall | 1 | x | 2 | 4.2 |  | 1.4 | 11.76
| GF Gents Rear side wall | 1 | x | 1 | 2.72 |  | 1 | 2.72
| GF Gents toilet wall | 1 | x | 1 | 2.72 |  | 1.55 | 4.216
| Add jams | 1 | x | 2 | 1.4 | 0.15 |  | 0.42
| Door top wall | 1 | x | 1 | 2.72 |  | 0.6 | 1.632
| Inbetween wall | 1 | x | 2 | 1.25 |  | 0.6 | 1.5
| GF Ladies toilet wall inner | 1 | x | 2 | 4.2 |  | 1.4 | 11.76
| GF Ladies toilet rear side wall | 1 | x | 1 | 1.95 |  | 1 | 1.95
| GF Ladies toilet front side wall | 1 | x | 1 | 1.95 |  | 0.6 | 1.17
| GF Gents single toilet wall | 1 | x | 1 | 10.6 |  | 1.4 | 14.84
| Door top wall | 1 | x | 1 | 1.25 |  | 0.6 | 0.75
| GF Inbetween Reception and Bank wall | 1 | x | 1 | 5.45 |  | 2.9 | 15.805
| GF,FF,Gents toilet ceiling | 1 | x | 2 | 4.2 | 2.72 |  | 22.848
| GF,FF,Ladies toilet ceiling | 1 | x | 2 | 4.2 | 1.95 |  | 16.38
| GF,FF,Gents single toilet ceiling | 1 | x | 2 | 4.2 | 1.1 |  | 9.24
False ceiling bottom
| FF Office hall | 1 | x | 1 | 16.4 | 17.5 |  | 287
| FF Office hall offset | 1 | x | 1 | 11.5 | 1.5 |  | 17.25
| FF Office hall offset | 1 | x | 1 | 5.4 | 1.5 |  | 8.1
| MD Room | 1 | x | 1 | 7.3 | 5.6 |  | 40.88
| Rest room 1 | 1 | x | 1 | 5.9 | 2.5 |  | 14.75
| Rest room 2 | 1 | x | 1 | 2.85 | 3 |  | 8.55
| Visiter | 1 | x | 1 | 5.8 | 3.85 |  | 22.33
| Old GM Room | 1 | x | 1 | 3.55 | 4.3 |  | 15.265
| Rest room | 1 | x | 1 | 2.5 | 1.5 |  | 3.75
| AGM 1,2,3 | 1 | x | 3 | 5.85 | 2.95 |  | 51.7725
| New GM, room | 1 | x | 1 | 5.41 | 3.425 |  | 18.5293
| D/f Toliet | -1 | x | 1 | 1.63 | 2 |  | -3.26
| New CR room | 1 | x | 1 | 4.45 | 5.41 |  | 24.0745
| D/f Toliet | 1 | x | 1 | 1.5 | 2 |  | 3
| ATM | 1 | x | 1 | 4 | 4 |  | 16
| ATM center | 1 | x | 1 | 0.9 | 2.9 |  | 2.61
| Atm center alround | 1 | x | 1 | 3.6 | 0.1 |  | 0.36
| GM front extra | 1 | x | 1 | 8.5 | 0.4 |  | 3.4
| FF Toilet verandha | 1 | x | 1 | 6 | 2.65 |  | 15.9
| GF Reception area | 1 | x | 1 | 6.2 | 5.7 |  | 35.34 |  | #REF!
| FF Reception area | 1 | x | 1 | 6.2 | 5.7 |  | 35.34
| G.F ,FF Landing | 1 | x | 2 | 3.75 | 3.75 |  | 28.125
| S.F Chairman room | 1 | x | 1 | 5.95 | 5.95 |  | 35.4025
| Rest room | 1 | x | 1 | 2.92 | 2.92 |  | 8.5264
| Meeting hall | 1 | x | 2 | 5.8 | 3.1 |  | 35.96
| Meeting hall | 1 | x | 1 | 7.3 | 5.42 |  | 39.566
| Waiting room | 1 | x | 1 | 4.3 | 2.85 |  | 12.255
| Computer room | 1 | x | 1 | 8.9 | 5.85 |  | 52.065
| AC Duct portion | 1 | x | 2 | 10.75 | 1.05 |  | 22.575
[7 empty] | Total | 1653.6411
[7 empty] | Say | 1653.65 | M2
2 | Painting two coats of Interior Emulsion paint including labour charges and materials etc all complete
False ceiling bottom
| FF Office hall | 1 | x | 1 | 16.4 | 17.5 |  | 287
| FF Office hall offset | 1 | x | 1 | 11.5 | 1.5 |  | 17.25
| FF Office hall offset | 1 | x | 1 | 5.4 | 1.5 |  | 8.1
| MD Room | 1 | x | 1 | 7.3 | 5.6 |  | 40.88
| Rest room 1 | 1 | x | 1 | 5.9 | 2.5 |  | 14.75
| Rest room 2 | 1 | x | 1 | 2.85 | 3 |  | 8.55
| Visiter | 1 | x | 1 | 5.8 | 3.85 |  | 22.33
| Old GM Room | 1 | x | 1 | 3.55 | 4.3 |  | 15.265
| Rest room | 1 | x | 1 | 2.5 | 1.5 |  | 3.75
| AGM 1,2,3 | 1 | x | 3 | 5.85 | 2.95 |  | 51.7725
| New GM, room | 1 | x | 1 | 5.41 | 3.425 |  | 18.5293
| D/f Toliet | -1 | x | 1 | 1.63 | 2 |  | -3.26
| New CR room | 1 | x | 1 | 4.45 | 5.41 |  | 24.0745
| D/f Toliet | 1 | x | 1 | 1.5 | 2 |  | 3
| ATM | 1 | x | 1 | 4 | 4 |  | 16
| ATM center | 1 | x | 1 | 0.9 | 2.9 |  | 2.61
| Atm center alround | 1 | x | 1 | 3.6 | 0.1 |  | 0.36
| GM front extra | 1 | x | 1 | 8.5 | 0.4 |  | 3.4
| FF Toilet verandha | 1 | x | 1 | 6 | 2.65 |  | 15.9
| GF Reception area | 1 | x | 1 | 6.2 | 5.7 |  | 35.34
| FF Reception area | 1 | x | 1 | 6.2 | 5.7 |  | 35.34
| G.F ,FF Landing | 1 | x | 2 | 3.75 | 3.75 |  | 28.125
| S.F Chairman room | 1 | x | 1 | 5.95 | 5.95 |  | 35.4025
| Rest room | 1 | x | 1 | 2.92 | 2.92 |  | 8.5264
| Meeting hall | 1 | x | 2 | 5.8 | 3.1 |  | 35.96
| Meeting hall | 1 | x | 1 | 7.3 | 5.42 |  | 39.566
| Waiting room | 1 | x | 1 | 4.3 | 2.85 |  | 12.255
| Computer room | 1 | x | 1 | 8.9 | 5.85 |  | 52.065
| GF,FF,Gents toilet ceiling | 1 | x | 2 | 4.2 | 2.72 |  | 22.848
| GF,FF,Ladies toilet ceiling | 1 | x | 2 | 4.2 | 1.95 |  | 16.38
| GF,FF,Gents single toilet ceiling | 1 | x | 2 | 4.2 | 1.1 |  | 9.24
| AC Duct portion | 1 | x | 2 | 10.75 | 1.05 |  | 22.575
[7 empty] | Total | 903.8842
[7 empty] | Say | 903.9 | M2
3 | Supply and fixing of calcium silicate board panelling with required spacing horizondaly and verticaly 25 x 50 mm channels using and fixed with necessary screws and joint filt with sealant of dow corning 789 or equialant sealant and the required area as directed by departmental officers the rate inclusive of all materials ,labour ,power and conveniyence of materilas to the work site loading and unloading etc
| MD Rest partition | 1 | x | 1 | 5.45 |  | 2.85 | 15.5325
| Inbetween MD Rest and hall partition | 1 | x | 1 | 2.38 |  | 2.85 | 6.783
| D/f Rest room flush door | -1 | x | 1 | 0.85 |  | 2.25 | -1.9125
| PC room Left side partition | 1 | x | 1 | 5.45 |  | 2.85 | 15.5325
| D/f Door | -1 | x | 1 | 1.3 |  | 2.34 | -3.042
| Pc Front partition | 1 | x | 1 | 3.45 |  | 2.85 | 9.8325
| D/f Door | -1 | x | 1 | 1.2 |  | 2.25 | -2.7
| I/B wall pc and computer partition | 1 | x | 1 | 4.25 |  | 2.85 | 12.1125
| D/f door | -1 | x | 1 | 0.9 |  | 2.25 | -2.025
| Hall partition | 1 | x | 2 | 5.48 |  | 2.85 | 31.236
| D/f Door | -1 | x | 1 | 1.4 |  | 2.25 | -3.15
| FF Front Entrnce Partition | 1 | x | 2 | 5.48 |  | 2.85 | 31.236
| D/f Door | -2 | x | 2 | 1.45 |  | 2.25 | -13.05
[7 empty] | Total | 96.3855
[7 empty] | Say | 96.4 | M2
4 | Supply and fixing of Flush door size ( 1200 x 2400 mm ) single leaf including labours and materials etc all complete.
| MD Main door | 1 | x | 1 | 1.2 |  | 2.25 | 2.7
[7 empty] | Total | 2.7 | M2
5 | Supply and fixing of Flush door size ( 900 x 2400 mm ) single leaf including labours and materials etc all complete.
| MD Rest room Door | 1 | x | 1 | 0.9 |  | 2.25 | 2.025
[7 empty] | Total | 2.025
[7 empty] | Say | 2.05 | M2
6 | Supply and fixing of Teak wood Glass door size (1500 x 2400 mm ) Double leaf including labours and materials etc all complete.
| FF Office hall Entrance door | 1 | x | 1 | 1.35 |  | 2.25 | 3.0375
[7 empty] | Total | 3.0375
[7 empty] | Say | 3.05 | M2
7 | Supply and fixing of TW Wrought and put up including labour charges etc all complete
a) | T.W.SCANTLING 2M-3M LONG
| FF Main door vertical | 2 | x | 2 | 0.25 | 0.1 | 0.075 | 0.0075
[7 empty] | Total | 0.01 | M3
b) | T.W.SCANTLING UP TO 2M LONG
| FF Main door vertical | 2 | x | 2 | 2 | 0.1 | 0.075 | 0.06
| FF Main door horizondal | 1 | x | 2 | 1.45 | 0.1 | 0.075 | 0.02175
[7 empty] | Total | 0.08175 | M3
8 | Supply and fixing of Aluminium Hydralic door closer including materials and labour charges etc all complete
| FF Office entrance door | 1 | x | 2 |  |  |  | 2
| MD room door | 1 | x | 1 |  |  |  | 1
| MD Rest room door | 1 | x | 1 |  |  |  | 1
[7 empty] | Total | 4 | Nos
9 | Supply and installation of 4 KVA capacity automatic voltage Stablizer with time delay relay etc all complete
| FF Office hall | 1 | x | 7 |  |  |  | 7
| CR room | 1 | x | 1 |  |  |  | 1
| GM | 1 | x | 1 |  |  |  | 1
| MD room | 1 | x | 2 |  |  |  | 2
| ATM | 1 | x | 1 |  |  |  | 1
[7 empty] | Total | 12 | Nos
10 | Supply and installation of 5 KVA capacity automatic voltage Stablizer with time delay relay etc all complete
| ATM | 1 | x | 1 |  |  |  | 1
[7 empty] | Total | 1 | No
11 | Supply and fixing of Glavanum sheet 0.47 mm thick etc all complete
| For Stair case terrace | 1 | x | 1 | 6.5 | 3 |  | 19.5
[7 empty] | Total | 19.5 | M2
12 | Supplying and fixing in position of UPVC Ventilator louvered ventilator type for all sizes etc all complete
| G.F Toilet | 1 | x | 5 | 0.6 |  | 0.6 | 1.8
| F.F Computer room | 1 | x | 1 | 0.9 |  | 0.6 | 0.54
| MD Toilet | 1 | x | 1 | 0.9 |  | 0.6 | 0.54
[7 empty] | Total | 2.88
[7 empty] | Say | 2.9 | M2
13 | Supplying and fixing in position of UPVC window of casement type( open) for all sizes etc all complete
| Guard room window | 1 | x | 1 | 0.6 |  | 1.35 | 0.81
| Guard room window | 1 | x | 1 | 1.58 |  | 1.28 | 2.0224
| Guard room window | 1 | x | 2 | 0.6 |  | 1.05 | 1.26
[7 empty] | Total | 4.0924
[7 empty] | Say | 4.1 | M2
14 | Supply and fixing of Healthfauct hose including materials etc all complete
| S.F in bank toilet | 1 | x | 8 |  |  |  | 8
| F.F in bank toilet | 1 | x | 8 |  |  |  | 8
| G.F in bank toilet | 1 | x | 6 |  |  |  | 6
[7 empty] | Total | 22 | Nos
15 | Supplying and fixing the wall Panelling fixing the water proof plywood 9mm thick board over the country wood planks. Over the plywood OST sheet of 4mm thick will be fixed with necessary screws and fevicol giving neat finish
| Ground floor Reception area | 1 | x | 1 | 7.5 |  | 3 | 22.5
[7 empty] | Total | 22.5
16 | Supply and fixing of 12 mm thick Toughened Glass door with including handle ,hinges,lock,base pinplate all materials and tools ,Transportation charges etc all complete
| Reception door | 1 | x | 1 | 2.4 |  | 2.1 | 5.04
[7 empty] | Total | 5.04
[7 empty] | Say | 5.05
17 | Providing wooden MELAMEN DOOR POLISH for new door including labour charges etc all complete
| FF Entrance door | 1 | x | 2 | 1.5 | 2.25 | 2.4 | 16.2
| MD Room | 1 | x | 1 | 1.2 | 2.25 | 2.4 | 6.48
| MD Rest room | 1 | x | 1 | 0.9 | 2.25 | 2.4 | 4.86
[7 empty] | Total | 27.54
[7 empty] | Say | 27.55
18 | Supply and fixing of ms rectanular square pipe size 70x30x2.9 mm etc all complete
| For horizondal | 1 | x | 4 | 3 |  |  | 12
| For horizondal | 1 | x | 3 | 6.5 |  |  | 19.5
[7 empty] | Total | 31.5
| Weight calculation (70x30x2.9 mm) = 4.12 kg/rmt |  |  |  | 31.5 | x | 4.12 | 129.78
[7 empty] | Say | 129.8
19 | Labour charges for truss iron works etc all complete
| As per item, No: 18 | [6 empty] | 129.8
[7 empty] | Total | 129.8

## Abs (2)
Name of work : Providing Modular section cabin and cupboard arrangements for the work of special repair works for central co operative bank building at Vannarapettai in Tirunelveli district.
ABSTRACT
SL.No |  | Qty | Units | Rate | Amount | 2 | 5000 | 10000
1 | Removing Existing aluminium partition wall etc all complete |  | Sqm | 3875 | 0 | 5 | 5720 | 28600
2 | One coat putty etc all complete |  | Sqm | 1500 | 0 | 1 | 7400 | 7400
3 | Supply and fixing of health closet etc all complete |  | Nos | 1013 | 0 | 1 | 7100 | 7100
|  |  |  | SR P/57 22-23 |  | 102 | 19 | 1938
4 | Supply and fixing of long body tap etc |  | Nos | 1750 | 0 | 1 | 3024 | 3024
5 | Supply and fixing of Short body tap etc |  | Nos | 7500 | 0 | 1 | 4200 | 4200
6 | Painting the wall with Texture finish paint incluidng labour charge etc all complete |  | Nos | 412 | 0 | 1 | 18500 | 18500
|  |  |  | SR P/45 22-23 |  | 8 | 116.9 | 935.2
7 | Supply and fixing of Mico board etc all complete |  |  |  |  | 1 | 342 | 342
8 | Supplying and fixing of AC copper pipe etc all complete |  |  |  |  | 1 | 22500 | 22500
9 | Labour charges for 2 ton AC water wash service etc all complete |  |  |  |  | 40 | 33 | 1320
10 | Labour charges and Erection charges for 2 ton and 1.5 ton AC unit etc all complete |  |  |  |  | 102 | 9.5 | 969
11 | Supply and fixing of AC unit stand outer etc all complete |  |  |  |  | 7 | 120 | 840
12 | Supply and delivery of 4 KVA Steplessar for AC unit etc all complete |  |  |  |  | 7 | 261.6 | 1831.2
13 | Run off 8 swg 4 wires of 4 sqmm etc all complete | [5 empty] | Total | 109499.4
14 | Old septick tank cleaning work etc all complete | [5 empty] | 12% | 13139.928
15 | Atm stickering works etc all complete | [5 empty] | Total | 122639.328
16 | Tree cutting works and cleaning works etc
17 | Fixing charges for existing aluminium door works etc all complete
18 | Existing compound wall white washing painting works
19 | Machineries works for cleaning works and existing road formation in raining season
| Total |  |  |  | 0
| GST @ 18% |  |  |  | 0
| Grand Total |  |  |  | 0
| Labour welfare fund 1 % |  |  |  | 0
| Supervision charges 7.5 % |  |  |  | 0
| Supervision charges Gst 18% |  |  |  | 0
| Total |  |  |  | 0

## Data
TAMIL NADU POLICE HOUSING CORPORATION
======================================
PLACE:- |  | Chennai |  | 2023-2024
- | - | - | - | - | -
QTY |  | COST OF MATERIALS | RATE | PER | AMOUNT
- | - | - | - | - | -
| * | CEMENT MORTAR(1:1.5)
-
0.96 | M.T | CEMENT | 6040 | M.T | 5798.4
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 7594.28
-
| * | CEMENT MORTAR(1:2)
-
0.72 | M.T | CEMENT | 6040 | M.T | 4348.8
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 6144.68
-
| * | CEMENT MORTAR(1:3)
-
0.48 | M.T | CEMENT | 6040 | M.T | 2899.2
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 4695.08
-
| * | CEMENT MORTAR(1:4)
0.36 | M.T | CEMENT | 6040 | M.T | 2174.4
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 3970.28
-
| * | CEMENT MORTAR(1:5)
-
0.288 | M.T | CEMENT | 6040 | M.T | 1739.52
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 3535.4
-
| * | CEMENT MORTAR(1:6)
-
0.24 | M.T | CEMENT | 6040 | M.T | 1449.6
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 3245.48
-
| * | CEMENT MORTAR(1:7)
-
0.206 | M.T | CEMENT | 6040 | M.T | 1244.24
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 3040.12
-
| * | CEMENT MORTAR(1:8)
-
0.18 | M.T | CEMENT | 6040 | M.T | 1087.2
1 | CUM | SAND | 1674.08 | CUM | 1674.08
1 | CUM | MIXING OF MORTAR | 121.8 | CUM | 121.8
| L.S | SUNDRIES |  | L.S | 0
-
|  | TOTAL FOR 1 CUM |  |  | 2883.08
-
ONE COAT OF WALL PATTY CHENNAI CITY
PATTY (p-45/151)
5 | Kg | White wall putty powder | 27.45 | Kg | 137.25
1 | No | Painter - I st Class | 836.85 | No | 836.85
| LS | SUNDRIES |  | LS | 17.67
|  | Rate for 10 Sqm |  |  | 991.77
|  | Rate for 1 Sqm |  |  | 99.18
40. | * | PAINTING TWO COATS OVER NEW (as per CER-112/2007-08)
PLASTERED SURFACE WITH
Plastic Emulsion PAINT
-
1.4 | LIT | Plastic Emulsion PAINT (LMR item 113) p-45 143( First qty | 295.6 | LIT | 413.84
0.98 | LIT | Primer (LMR item 142) p45 | 147.5 | LIT | 144.55
2.2 | NO | PAINTER I | 836.85 | NO | 1841.07
| L.S | SUNDRIES FOR BRUSHES,ETC |  | L.S | 2.55
|  | TOTAL FOR 10 SQM |  |  | 2402.01
-
|  | RATE PER SQM |  |  | 240.2
Flush door shutter size 1200x2400 ( Single leaf)
|  | shutter size 1200x2400 =1.1 x 2.325 =2.56 | 2.56
2.56 | SQM | Solid core flush door shutter with TW palin | 2255 | SQM | 5772.8
2.56 | SQM | Labour for Wrought & Putup (SR P.32,it-156a) | 224.81 | SQM | 575.51
2 | NO | Door Handle with CP screws 6' | 57.65 | NO | 115.3
3 | NO | 5" Butt Hings | 89.6 | NO | 268.8
2 | NO | 6"x1/2" Tower Bolt | 64.8 | NO | 129.6
1 | NO | 10"x5/8" Aldrop | 181 | NO | 181
92 | NO | Brass Screws | 2.41 | NO | 221.72
1 | NO | Rubber bush | 23.1 | NO | 23.1
1 | NO | Door Stopper | 49.55 | NO | 49.55
| SQM | Varnish Two Coats | 241.31 | SQM | 0
|  | Rate for 2.56 Sqm |  |  | 7337.38
|  | Rate for 1 Sqm |  |  | 2866.16
Flush door shutter size 900x2400 ( Single leaf)
|  | Shutter size (0.8 x 2.325) | 1.86
1.86 | SQM | Solid core flush door shutter with TW palin | 2255 | SQM | 4194.3
1.86 | SQM | Labour for Wrought & Putup | 224.81 | SQM | 418.15
2 | NO | Door Handle with CP screws 6' | 57.65 | NO | 115.3
4 | NO | 5" Butt Hings | 89.6 | NO | 358.4
2 | NO | 6"x1/2" Tower Bolt | 64.8 | NO | 129.6
1 | NO | 10"x5/8" Aldrop | 181 | NO | 181
92 | NO | Brass Screws | 2.41 | NO | 221.72
1 | NO | Rubber bush | 23.1 | NO | 23.1
1 | NO | Door Stopper | 49.55 | NO | 49.55
0.39 | SQM | Painting Two Coats | 241.31 | SQM
|  | Rate for 1.86 Sqm |  |  | 5691.12
|  | Rate for 1 Sqm |  |  | 3059.74
21.2 |  | TEAK WOOD WROUGHT & PUT UP
-
| A | T.W.SCANTLING 2M-3M LONG
-
1 | CUM | LABOUR CHARGE FOR WROUGHT & PUTUP | 14374.5 | CUM | 14374.5
1 | CUM | T.W.SCANTLING 2M-3M LONG | 111600 | CUM | 111600
=
|  | RATE FOR T.W.SCANDLING 2M-3M LONG |  |  | 125974.5
=
| B | T.W.SCANTLING UP TO 2M LONG
-
1 | CUM | LABOUR CHARGE FOR WROUGHT & PUTUP | 14374.5 | CUM | 14374.5
1 | CUM | T.W.SCANTLING 2M-3M LONG | 99400 | CUM | 99400
=
|  | RATE FOR T.W.SCANTLING 2M LONG |  |  | 113774.5
=
SUPPLY AND FIXING OF GALVANIUM SHEET 0.47MM THICK
11 | Sqm | GALVANIUM SHEET 0.47MM THICK ( SR p-72) | 434 | Sqm | 4774
2.2 | Each | FITTER I st CLASS | 925.05 | Each | 2035.11
1.1 | Each | CARPENTER I ST CLASS | 1024.8 | Each | 1127.28
3.2 | Each | MAZDOOR I ST CLASS | 683.55 | Each | 2187.36
| L.S | Bolts & Washers | L.S |  | 107.11
|  | Rate For 10 Sqm |  |  | 10230.86
|  | Rate For 1 Sqm |  |  | 1023.09
OBESERVED DATA
| * | T.W.DOUBLE LEAF fullY Glazed
DOOR SHUTTER FOR DOOR OF SIZE
1500 X 2400MM
-
|  | SHUTTER SIZE-1X2X.675X2.3125 | = | 3.122 | Sqm
|  | STYLES(OVER 2M) -2X2X2.3125X0.15X0.0375 = 0.052 | = | 0.052 | Cum
RAILS(BELOW 2M)-
|  | TOP - 1X2X0.675X0.150X0.0375 |  | 0.0076
|  | Bottom AND TOP - 1X2X0.675X0.150X0.0375 = 0.0076 | = | 0.0076
-----------------
|  |  |  | 0.0152 | Cum
-----------------
|  | 5.5 MM THK. GLASS -2X1X0.40X1.85 |  | 1.48 | Sqm
|  | T.W. Beeding Vertical- 2 x 2 x 1.975 |  | 7.9
|  | T.W. Beeding Horizontal- 2 x 2 x 0.40 |  | 1.6
|  |  |  | 9.5 | rmt
0.052 | CUM | T.W SCANTLING ABOVE 2M LONG | 111600 | CUM | 5803.2
0.0152 | CUM | T.W SCANTLING BELOW 2M LONG | 99400 | CUM | 1510.88
1.48 | SQM | 5.5 MM THICK PLAIN GLASS p44 sl.137 | 562.5 | SQM | 832.5
9.5 | RMT | T.W. beeding 15mm x 12 mm p42 113a | 15.45 | Rmt | 146.775
3.122 | SQM | LABOUR FOR WROUGHT&PUTUP p33 sl.146 /4 | 1430.1 | SQM | 4464.7722
4 | NOS | DOOR HANDLE Mejastic | 450 | Each | 1800 | 4 | NOS | DOOR HANDLE Mejastic | 450 | Each | 1800
8 | NOS | 6" Brass HINGES | 79 | Each | 632 | 8 | NOS | 6" Brass HINGES | 79 | Each | 632
4 | NOS | 8" BRASS TOWER BOLTS | 130 | Each | 520 | 4 | NOS | 8" BRASS TOWER BOLTS | 130 | Each | 520
1 | NOS | Mortice lock with handle | 985 | Each | 985 | 1 | NOS | Mortice lock with handle | 985 | Each | 985
2 | NOS | RUBBER BUSH | 23.1 | Each | 46.2 | 2 | NOS | RUBBER BUSH | 23.1 | Each | 46.2
2 | NOS | DOOR STOPPER | 49.55 | Each | 99.1 | 2 | NOS | DOOR STOPPER | 49.55 | Each | 99.1
130 | NOS | Brass screw | 2.41 |  | 313.3 | 130 | NOS | Brass screw | 2.41 |  | 313.3
-
|  | TOTAL FOR 3.122 SQM |  |  | 17153.7272
-
|  | RATE PER SQM |  | Rs. | 5494.4674
Providing wall panelling using 12mm BWR plywood over 2"x1" aluminium channel to be fixed on wall
12.72 | Kg | Aluminium section [SR P.44] | 347.7 | Kg | 4422.74
9.4 | Sqm | 12mm thk. BWR plywood board (Qtn) | 807 | Sqm | 7585.8
9.4 | Sqm | 1mm thick laminated sheet [SR P.55] | 412 | Sqm | 3872.8
40 | nos | MS clips | 10 | nos | 400
2.25 | Kg | Fevicol [SR P.39] | 199.75 | Kg | 449.44
9.4 | Sqm | labour charges | 2891.18 | Sqm | 27177.09
0.25 | Kg | Nails [SR P.42] | 64 | Kg | 16
|  | Rate For 9.40 Sqm |  |  | 43923.87
|  | Say | Rate Per Sqm |  | 4672.75
Labour Charges
1 | nos | Carpenter Ist Class | 1024.8 | nos | 1024.8
1.5 | nos | MAZDOOR I | 683.55 | nos | 1025.33
1.5 | nos | MAZDOOR II | 560.7 | nos | 841.05
2891.18
Providing wooden MELAMEN DOOR POLISH
For New Wood
Contain a size 1.2x2.1 m
Area of Polishing 1x1x2.25x1.2x2.1+5.67m2
|  | - | -
8 | NOS | Sand paper No 50 (Qtn) | 4.1 | Each | 32.8
8 | NOS | Sand paper No 80 | 3.69 | Each | 29.52
8 | NOS | Sand paper No 100 | 4.1 | Each | 32.8
0.75 | Kg | Wooden filter | 176.4 | Each | 132.3
2.25 | liter | sand seal thinner | 140.41 | liter | 315.92
4.5 | liter | Thinner | 65 | liter | 292.5
6 | NOS | Water Emery No 250 | 8 | Each | 48
6 | NOS | Water Emery No 320 | 8.61 | Each | 51.66
4 | NOS | Water Emery No 400 | 8.61 | Each | 34.44
300 | gm | Teak Powder | 30 | 100gm | 90
300 | gm | Red Powder | 44.99 | 500gm | 26.99
1.5 | Kg | Fresh Chalk Powder | 20.95 | Kg | 31.43
2.25 | liter | MELAMEN matt Qtn | 212.41 | liter | 477.92
0.75 | liter | MELAMEN Glozy | 205.21 | liter | 153.91
2.25 | liter | Thinner 106 | 185.21 | liter | 416.72
500 | gm | Banian waste | 52.25 | Kg | 26.13
1 | NOS | 3" Brush | 131.21 | 1No | 131.21
1 | NOS | 2" Flat Brush | 12.3 | 1No | 12.3
4 | NOS | PAINTER- I Class | 836.85 | Each | 3347.4
2 | NOS | PAINTER - II Class | 810.6 | Each | 1621.2
2 | NOS | Mazdoor - II Class | 560.7 | Each | 1121.4
|  | Bladder & Tools |  |  | 20
----------------------
|  | TOTAL FOR 5.67 SQM |  |  | 8446.55
=
|  | Rate for 1 Sqm |  |  | 1489.69
39 |  | Steel grill for Verandah Enclousure PWD SR p20/ Item 138/131 | 70.15 | Kg | 70.15

## lead
Tamil Nadu Police Housing Corparation Ltd.
==========================================================
PLACE:- | Tirunelveli |  | 2023-2024
| - | - | - | - | - | - | - | - | - | - | -
SL.NO | DESCRIPTION OF MATERIALS | UNIT | SOURCE | Total | COST OF | LEAD | Add 10% | UN LO- | MATERIAL | LABOUR RATE
|  |  |  | Lead | MATERIAL | CHARGE | for quarry at | ADING | COST @ SITE
- | - | - | - | - | - | - | Thuvakudi | - | - | - | -
1. | ROUGH STONE sl.37 p15 | CUM. | Thalaiyuthoo | 10 | 449.4 | 116.5 |  | 0 | 565.9 | MASON-I Brick / Stone work (p-10) | 1048.95
2. | BOND STONE sl.44 p16 | CUM. | Thalaiyuthoo | 10 | 648.4 | 116.5 |  | 0 | 764.9 | MASON-II Brick / Stone work (p-10) | 978.6
3. | HARD BROKEN STONE JELLY 3mm To 10mm p-16(53-55) | CUM. | Thalaiyuthoo | 10 | 773.67 | 116.5 |  | 0 | 890.17 | MAZDOOR-I (p-11) | 683.55
4. | HARD BROKEN STONE JELLY 10mm | CUM. | Thalaiyuthoo | 10 | 1016 | 116.5 |  | 0 | 1132.5 | MAZDOOR-II (p-12) | 560.7
5. | HARD BROKEN STONE JELLY 12mm | CUM. | Thalaiyuthoo | 10 | 1382 | 116.5 |  | 0 | 1498.5 | PAINTER-I (p-10) | 836.85
6. | HARD BROKEN STONE JELLY 20mm | CUM. | Thalaiyuthoo | 10 | 1489 | 116.5 |  | 0 | 1605.5 | PAINTER-II (p-11) | 810.6
7. | HARD BROKEN STONE JELLY 40mm | CUM. | Thalaiyuthoo | 10 | 1069.8 | 116.5 |  | 0 | 1186.3 | PLUMBER-I (p-10) | 909.3
8. | SAND FOR MORTAR sl.100 p20 | CUM. | Seliyanallur | 34 | 1338 | 336.08 |  | 0 | 1674.08 | PLUMBER-II (p-11) | 880.95
9. | SAND FOR FILLING (Ann IV) | CUM. | Seliyanallur | 34 | 1338 | 336.08 |  | 0 | 1674.08 | FITTER-I (p-9) | 925.05
10. | Kiln Burnt Country Bricks SIZE 22x11x7Cm p-14 it-5a | 1000nos. | Vellakovil | 6 | 5709 | 58.92 |  | 0 | 5767.92 | FITTER-II (p-11) | 898.8
11. | BRICK JELLY 40mmGAUGE p-14 it-10 a | CUM | Vellakovil | 6 | 705 | 47.94 |  | 0 | 752.94 | CARPENTER-I (p-10) | 1024.8
12. | BRICK JELLY 20mmGAUGE | CUM | Vellakovil | 6 | 786 | 47.94 |  | 0 | 833.94 | CARPENTER-II (p-11) | 978.6
13. | MACHINE PRESSED TILES 23x 23x 2 Cm p-15 It-20 | 1000nos. | Local | 0 | 16106 | 0 |  | 0 | 16106 | STONE CUTTER-I (p-9) | 804.3
14. | SLACKED SHELL LIME sl.89 p17 | CUM. | Local |  | 1348 |  |  | 0 | 1348 | STONE CUTTER-II | 774.9
15. | SLACKED &SREENED LIME STONE sl107/67 | CUM. | Thachanallur | 6 | 993 | 47.94 |  | 0 | 1040.94 | FLOOR POLISHER | 807.45
16. | C.W SCANTLING UPTO 4M LONG p-21 it-127 | CUM. | local | 0 | 34300 | 0 |  | 0 | 34300 | Mortar mix charges manual sl.125(Ann3 N-29) | 121.8
17. | C.W. PLANK UPTO 40mmTHICK UPTO 30 Cm WIDTH | CUM. | local | 0 | 39400 | 0 |  | 0 | 39400 | Vibrat-charges(R.C.C) sl.71/2 p25 | 98.91
18. | T.W SCANTLING 2M TO 3M LONG 112/73 p-21 | CUM. | local | 0 | 111600 | 0 |  | 0 | 111600 | Vibrat-charges(P.C.C) sl.71/1 p25 | 73.29
19. | T.W.SCANTLING BELOW 2M LONG 113/74 p-21 | CUM. | local | 0 | 99400 | 0 |  | 0 | 99400 | Sand filling charges sl.46/84p23 | 35.91
20. | T.W.PLANKS 15TO30cm WIDTH & 12to25mm Thick it-119 p-21 | CUM. | local | 0 | 95000 | 0 |  | 0 | 95000 | Earth filling charges sl.46/85 p23 | 40.9
21. | Country BricksKiln Burnt of SIZE 22x11x5Cm (7c)p-14 | 1000nos. | Vellakovil | 6 | 4299 | 58.92 |  | 0 | 4357.92 | E.W. 40/62 p-22 | 117.65
22. | MOSAIC TILES GRAY 25X25X2cm.it-30 p-17 | 1000nos. | local |  | 11907 |  |  | 0 | 11907 | L.C.T.W.Door- 104/2 p-27 | 1613.85
23. | CEMENT (supply at site) | M.T | local | 0 | 6040 | 0 |  |  | 6040 | L.C.marine doors-105/3 p-27 | 1345.05
24. | R.T.S. / M.S upto 16mm | M.T | Local | 0 | 58000 | 0 |  | 0 | 58000 | TW glazed window 109/8 p-27 | 1507.8
25. | M.S./ R.T.S above 16mm | M.T | Local | 0 | 58000 | 0 |  | 0 | 58000 | Wrought&putup 103/1 p-27 | 14374.5
26. | Country BricksKiln Burnt SIZE 22x11x5Cm | 1000nos. | Vellakovil | 6 | 4299 | 58.92 |  | 0 | 4357.92 | Ventilator 113/14 p-28 | 1256.85
27. | HBSJ 11.2mm IRC metal (SR 22-23,p16/48) | CUM. | Thalaiyuthoo | 10 | 961 | 116.5 |  |  | 1077.5 | Meter- Cupboard Weldmesh 118/23 p-28 | 1125.6
28. | HBSJ 37.5mm to 26.5mm IRC metal | CUM. | Thalaiyuthoo | 10 | 1082.5 | 116.5 |  | 0 | 1199 | E.W (SDR) 41/67 p-23 | 175.25
29. | HBSJ 63mm to 45mm IRC metal | CUM. | Thalaiyuthoo | 10 | 915.45 | 116.5 |  | 0 | 1031.95 | FITTER-II (Pipe & Bar Bend) 57/20a p-11 | 880.95
30. | Gravel p17 75 | CUM. | Adhichanallur | 19 | 222.7 | 206.14 |  | 0 | 428.84 | FITTER-I (Pipe & Bar Bend) 16/20A p-9 | 909.3
31 | Well Gravel p17 It76 | CUM. | Paruthiapdu | 23 | 166.5 | 241.81 |  | 0 | 408.31 | E.W loose soil p-22 SS20B/38/50 | 78.59
|  |  | - | [7 empty] | 0
| Chamber Burnt Bricks of size 23x11.2x7Cm p14/4b | 1000nos. | Vellakovil | 6 | 6595 | 98.22 | 0 | 0 | 6693.22 | LIFT CHARGES FOR B.W IN G.F * it-62/1 p-25 | 82.85
| Chamber Burnt Bricks of size 23x11.4x7.5Cmp14 /3a | 1000nos. | Vellakovil | 6 | 6795 | 98.22 | 0 | 0 | 6893.22 | LIFT CHARGES FOR B.W IN F.F * | 167.16
| Stone dust p17 item no-584 | Cum | Thalaiyuthoo | 10 | 123.7 | 79.9 | 0 | 0 | 203.6 | LIFT CHARGES FOR B.W IN S.F * | 167.16
| 6mmto 10mm HBG metal p-19 it-83+84/2 | Cum | Thalaiyuthoo | 10 | 851.5 | 116.5 | 0 | 0 | 968 | LIFT CHARGES FOR CONCRETE IN G.F *it-60/1 p-24 | 125.84
| Fly Ash Bricks it-3A/8a p-14 |  | Local | 6 | 6595 | 98.22 |  |  | 6693.22 | LIFT CHARGES FOR CONCRETE IN F.F * | 247.91
| Crushed Stone SAND FOR MORTAR sl.98/58C p20 | CUM. | Seliyanallur | 34 | 1338 | 336.08 |  | 0 | 1674.08 | LIFT CHARGES FOR CONCRETE IN S.F * | 247.91
| Crushed Stone SAND FOR FILLING | CUM. | Seliyanallur | 34 | 1338 | 336.08 |  | 0 | 1674.08 |  | 0
| - | - | - | - | - | - | - | - | - | - | 0
[10 empty] | SCRAPING THE OLD PLASTER SURFACE * p26/76/338 | 4.41
Certified that the lead particulars finished above correct to the best of my knowledge.
Certified that the presantly m sand from the approved source of seliyanallur which is nearest and 34 km from the site.