## Sheet1
TAMILNADU POLICE HOUSING CORPORATION LIMITED
CHENNAI DIVISION I
Name of work:- sports facilities for Resiential police public school campus at melakottaiur in chengalpattu dt
| F.S Value Rs: | 605 | lakhs
Sl. No | Name of work | Technical |  |  |  | Total | Further expenditure for complete project in all | Total Probable cost of the project | Probable savings ( A) | Probable Excess | Pecentage of Expenditure so for incurred to total | Percentage of work done with the total value
|  | So for accorded | To be accorded | Booked so for | Anticipated Expense/ Estimate | [8 empty] | 232.36
1 | Construction of Swimming Pool in Residential Police Public School Campus, Melakottaiyur in Chengalpattu District. | 252.61 |  | 190.52 | 47.03 | 237.56 |  |  | 19.2 | 3.79 | 15.41
2 | Construction of Building For Indoor games in Residential Police Public School Building at Melakottaiyur in Chengalpattu District. | 59.71 |  | 29.72 | 28.27 | 57.99 |  |  |  | 12.53 | -12.53 |  | 56.9914
3 | Formation of Tennis Court at the Residential Police Public School Campus , Melakottaiyur in Chengalpattu District | 19.98 |  | 0 | 18.78 | 18.78 |  |  | 1.19 | 0 | 1.19
4 | Formation of Concrete Basket Ball Court at the Residential Police Public School Campus , Melakottaiyur in Chengalpattu District | 12.64 |  | 0 | 11.87 | 11.87 |  |  | 0.77 | 0 | 0.77 |  |  | 11.8726
5 | Formation of Football Ground and Marking of Running track in the Football ground for the work of Construction of Residential Police Public School Building at Melakottaiyur in Chengalpattu District | 31.57 |  | 0 | 29.92 | 29.92 |  |  | 1.65 | 0 | 1.65 |  |  | 29.92
6 | Formation of Kids play area at the Residential Police Public School Campus , Melakottaiyur in Chengalpattu District | 7.91 |  | 5.9052 | 1.53 | 7.43 |  |  | 0.47 | 0 | 0.47 |  |  | 7.4343
|  | 384.42 |  | 226.15 | 137.41 | 363.56 |  |  |  |  | 6.97
| As per FS saving | 220.58
| As per WC saving | 6.97
247.54
246.55
1.5
0
0.09
0.67
7
2.38
4.5
[5 empty] | 0 | 5.05
[5 empty] | 0.78 | 10
0.48
[5 empty] | 0 | 27.7
4.52
7.59
1.19
8.38
5.42
31.85