## Namma School Namma Ooru Palli
Namma School Namma Ooru Palli Scheme
Progress Report for Construction of Toilet & other amenities for Government Schools
Sl.No | District | School Name | No. of units | FS Amount in Lakhs | Amount Received in Lakhs | Tender date | DHO | DDC | Physical percentage | Financial percentage | Present stage
Salem Division
1 | Ranipet | GMHSS, Panapakkam | 2 | 17.68 | 17.68 | 2023-08-17 | 03.09.2023 | 02.12.2023 | 40% | Bill not paid | Roof slab form work & steel fabrication work completed.
2 | Vellore | GGHSS Nadupet, Gudiyatham | 3 | 26.52 | 26.52 | 2023-08-17 | 23.09.2023 | 22.12.2023 | 5% | Bill not paid | Earth work excavation under progress.
3 | Villupuram | S.R.Government Girls Higher Secondary School, Valavanur | 2 | 17.68 | 17.68 | 2023-08-04 | 16.08.2023 | 15.11.2023 | 53% | 45% | Toilet block roof slab and septic tank cover slab concrtete laid.
30.11.2023
4 | Cuddalore | GGHSS - CHIDAMBARAM | 2 | 17.68 | 17.68 | 2023-05-25 | 12.07.2023 | 11.10.2023 | 70% | 52% | Inner plastering work is in progress.
31.10.2023
5 | Cuddalore | GGHSS - INDIRA NAGAR | 3 | 26.52 | 26.52 | 2023-05-25 | 03.07.2023 | 02.10.2023 | 81% | 66% | Inner partition wall lintel beam form work & steel fabrication work is under progress.
6 | Krishnagiri | GOVT GIRLS HSS, SHOOLAGIRI | 4 | 35.36 | 35.36 | 2023-07-05 | 07.08.2023 | 06.11.2023 | 47% | 30% | Roof slab form work is in progress.
7 | Krishnagiri | GOVT GIRLS HSS, DENKANIKOTTAI | 2 | 17.68 | 17.68 | 2023-07-05 | 19.07.2023 | 18.10.2023 | 42% | 40% | Roof slab & Septic tank Form and fabrication work is in progress.
31.12.2023
8 | Krishnagiri | GGHSS Hosur | 2 | 17.68 | 17.68 | 2023-07-27 | 07.08.2023 | 06.11.2023 | 60% | 45% | Outer plastering work is in progress.
31.12.2023
9 | Namakkal | GHSS, Kokkarayanpettai (Renovation work) |  | 12.5 | 12.5 | 2023-08-17 | 27.09.2023 | 26.12.2023 | 1% | Bill not paid | Footing PCC work is in progress.
10 | Dharmapuri | GHSS Elagiri | 2 | 17.68 | 17.64 | 2023-09-04 | 29.09.2023 | 28.12.2023 | 2% | Bill not paid | Footing form work & Fabrication work are in progress.
11 | Salem | GHSS Alagappampalayam Pudur | 2 | 17.68 | 17.68 | 2023-09-01 | 27.09.2023 | 26.12.2023 | 5% | Bill not paid | Earth work excavation under progress.
12 | Villupuram | GHSS Koliyanur | 2 | 17.68 | 17.68 | 2023-09-01 | __ | __ | __ | __ | Work order issued on 13.09.2023. Agreement to be executed. Tree uprooting work is in progress.
13 | Villupuram | GHSS Sithalingamadam | 2 | 17.68 | 17.68 | 2023-09-01 | 29.09.2023 | 28.12.2023 |  |  | Preliminary work is in progress.
14 | Kallakurichi | GHSS Manalurpet | 3 | 26.52 |  | 2023-10-18 | __ | __ | __ | __ | Tender fixed on 18.10.2023
15 | Krishnagiri | GGHSS Veppanapalli | 3 | 26.52 | 26.52 | 2023-09-20 | 2023-10-04 | 2024-01-03 | __ | __ | Work order issued on 03.10.2023. Agreement to be executed. Preliminary work is in progress.
16 | Vellore | GGHSS Latheri | 3 | 26.52 |  | 2023-09-20 | 2023-10-04 | 2024-01-03 | __ | __ | Work order issued on 03.10.2023. Agreement to be executed. Preliminary work is in progress.
17 | Thiruvannamalai | GHSS, Rajanthangal (Kilpennathur) | 1 | 11.14 | 11.14 | 2023-09-30 | 2023-10-04 | 2024-01-03 | __ | __ | Work order issued on 03.10.2023. Agreement to be executed. Preliminary work is in progress.
18 | Thiruvannamalai | GHSS, Nallavanpalayam (Renovation work) |  | 11.26 | 11.26 | 2023-09-30 | 2023-10-04 | 2024-01-03 | __ | __ | Work order issued on 03.10.2023. Agreement to be executed. Preliminary work is in progress.

## Sheet1 (hidden)
609101
361814
970915
72818.625
1043733.625 | 1118300 | 44237320.7
74566.375 | 6.6678
544280
1425324
1969604
147720.3
2117324.3 | 2286800
169475.7 | 7.411
582148
484813
1066961
80022.075
1146983.075 | 1457600
310616.925 | 21.3102 | 172383002
2098342
1579200 |  | 5101034
579481
2158681
161901.075
2320582.075 | 2481400 | 245202
160817.925 | 6.4809 | 2075678
5072633
931840 |  | 40120
491512 |  | 970915
1423352 |  | 187986926
106751.4 |  | 2135340
1530103.4 | 1639900 | 3033503
109796.6 | 6.6953 | 14099019.45
207254788.45
1774080 |  | 482144
324262 |  | 10710280
2098342 |  | 218447212.45
157375.65
2255717.65 | 2413900
158182.35 | 6.553
1085137
917160
2002297
150172.275
2152469.275 | 2468000
315530.725 | 12.7849
1104029
426559
1530588
114794.1
1645382.1 | 1766200
120817.9 | 6.8406
1435862
639816
2075678
155675.85
2231353.85 | 2410500
179146.15 | 7.4319
1537457
498611
2036068
152705.1
2188773.1 | 2361200
172426.9 | 7.3025
1250254
2689871
2699374
1501129
582252
1780341
1017976
44800
11565997
867449.775
12433446.775 | 14320300
1886853.225 | 13.1761
1427664
956344
2384008
178800.6
2562808.6 | 2703850
141041.4 | 5.2163
1300208
980632
2280840
171063
2451903 | 2599650
147747 | 5.6833
754137
459261
176202
525621
392969
2308190
173114.25
2481304.25 | 2545000
63695.75 | 2.5028
1169141
567261
137064
63407
1936873
145265.475
2082138.475 | 2245100
162961.525 | 7.2585
593740
572962
362549
1529251
114693.825
1643944.825 | 1814400
170455.175 | 9.3946
1117872
450277
1568149
117611.175
1685760.175 | 1811600
125839.825 | 6.9463
245202
18390.15
263592.15 | 317600
54007.85 | 17.005
9671714 | 96717.14
6635434.14
754865.62
390835.44
126633.44
119108
8026876.64
1444837.7952
9471714.4352
200000
9671714.4352
96717.1444
241792.8609
725378.5826
10735603.0231
50000
10785603.0231